## Form One
CROSS-LAND Construction
Project: | HARO SABU LELLO QAQE DS6 ROAD PROJECT
Client: | Oromia Roads Authority
Contractor: | Cross - Land Construction Pvt.Ltd.Co. | [7 empty] | Date |  |  |  | 2015-09-01 | [5 empty] | - | 2015-10-01
PROJECT: |  |  | HARO SABU LELLO QAQE DS6 ROAD PROJECT | [10 empty] | Budget Year |  |  |  | 2008 EC |  |  | Month No. |  |  | Month One
TIME | Initial |  | Extension | Total |  | Start |  |  | Completion |  |  | Elapsed |  | Remaining |  | Delay (days)
| 730 |  | 300 | 1030 |  | 2013-08-03 |  |  | 2016-05-29 |  |  |  | 76.6% |  | 23.4% | Until Last Month |  |  | This Month |  |  | Total
[12 empty] | 789 |  | 241 |  | 263.4654 |  |  | -0.18171 |  |  | 263.2837
AMOUNT | INCOME | Contract |  | Variation |  |  | Total |  |  | Until Last Month |  |  |  | This Month |  |  |  | To date |  |  |  | Remaining
[13 empty] | 51.02% |  |  |  | 1.4% |  |  |  | 52.42% |  |  |  | 47.58%
|  | 176814028 |  | 50654520.36 |  |  | 227468548.36 |  |  | 116060776.2395 |  |  |  | 3183964.49 |  |  |  | 119244740.7295 |  |  |  | 108223807.6305
| Payment Certified | IPC No | Date Approved | Gross |  |  | Previous Paid |  |  | Rebate |  | Retention |  |  | Loan |  | Advance Repaid |  |  | This Period |  |  | Net To date
|  | 15 | 2015-10-09 | 119244740.7295 |  |  | 116060776.2395 |  |  | 0 |  | 159198.2245 |  |  | 0 |  | 636792.898 |  |  | 2387973.3675 |  |  | 118448749.607
| COST | To date |  |  |  | Until Last Month |  |  |  |  | This Month |  |  |  |  | Pending Payment |  |  |  |  | 0
|  | 1189855.6537 |  | 100% |  |  |  |  | 0% |  | 1189855.6537 |  |  | 100%
|  | INCOME |  |  | COST |  |  | EVALUATION
[8 empty] | Programmed Status | [5 empty] | Saving/ (Overrun) | [5 empty] | 1295534.1444 |  |  |  | 52.13%
Schedule |  | 2075830.189 |  |  | 2485389.798 |  |  | Ahead of Schedule. | [5 empty] | Income - Cost (Actual) | [6 empty] | 1994108.8363
[8 empty] | Accelaration | [5 empty] | Deductions
Actual |  | 3183964.49 |  |  | 1189855.6537 |  |  | recorded was | [5 empty] | Advance Repaid |  |  |  | 20% | 636792.898 | Retention |  |  |  | 5% | 159198.2245
[8 empty] | equivalent to | [5 empty] | Loan |  |  |  | 0% | 0 | With Hold |  |  |  | 0% | 0
[8 empty] | 3.203 |  |  | days |  |  | Net Cash Inflow | [6 empty] | 1198117.7138
EXPENSES |  |  | EQUIPMENT
|  |  | Own |  |  | Rental |  |  |  | Spare Parts |  |  |  | Fuel |  |  |  | Lubricants |  |  |  | Total
|  |  | Amount |  | % | Amount |  |  | % | Amount |  |  | % | Amount |  |  | % | Amount |  |  | % | Amount |  |  | %
| Schedule |  | 1180449.1086 |  | 47.5% | 0 |  |  | 0% | 118044.9109 |  |  | 4.75% | 448196.3485 |  |  | 18.03% | 44819.6349 |  |  | 1.803% | 1791510.0029 |  |  | 72.08%
| Actual |  | 306107.6667 |  | 25.73% | 57300 |  |  | 4.816% | 35765 |  |  | 3.006% | 202878.19 |  |  | 17.05% | 0 |  |  | 0% | 602050.8567 |  |  | 50.6%
| Diff |  | 874341.4419 |  |  | -57300 |  |  |  | 82279.9109 |  |  |  | 245318.1585 |  |  |  | 44819.6349 |  |  |  | 1189459.1462
|  |  | MATERIAL |  |  |  | LABOUR | [14 empty] | OTHERS
[7 empty] | Basic + Pension |  |  |  |  | Overtime |  |  |  |  | Total
|  |  | Amount |  |  | % | Amount |  |  |  | % | Amount |  |  |  | % | Amount |  |  |  | % | Amount |  |  | %
| Schedule |  | 118044.9109 |  |  | 4.75% | 564334.8843 |  |  |  | 22.71% | 0 |  |  |  | 0% | 564334.8843 |  |  |  | 22.71% | 11500 |  |  | 0.4627%
| Actual |  | 35765 |  |  | 3.006% | 537757.2466 |  |  |  | 45.2% | 4282.5504 |  |  |  | 0.3599% | 542039.797 |  |  |  | 45.56% | 10000 |  |  | 0.8404%
| Diff |  | 82279.9109 |  |  |  | 26577.6377 |  |  |  |  | -4282.5504 |  |  |  |  | 22295.0874 |  |  |  |  | 1500
CRITICAL ISSUES
1 | EQUIPMENT MAINTENANCE | [6 empty] | 2 | CONTRACT ADMINISTRATION | [7 empty] | 3 | LOCAL PURCHASE & SUPPLY
No | Type of problem |  |  |  |  | Budget |  | No | Type of problem | [5 empty] | Budget |  | No | Type of problem | [5 empty] | Budget
1 | Delay Of Ordered Spare Parts | [6 empty] | 1 | ROW Problems Still Not Solved | [8 empty] | No Problem
2 | Generator Problem | [6 empty] | 2 | Subase Borrow Pit Site @ Stn 8 Is Still Not Hand Overed For The Contractor
[17 empty] | 4 | FOREIGN PURCHASE & SUPPLY
[17 empty] | No | Type of problem | [5 empty] | Budget
No Problem
5 | ADMINISTRATION & H R D | [6 empty] | 6 | CONSTRUCTION | [7 empty] | 7 | FINANCE
No | Type of problem |  |  |  |  | Budget |  | No | Type of problem | [5 empty] | Budget |  | No | Type of problem | [5 empty] | Budget
| No Problem | [6 empty] | 1 | Dozer For Excavation | [8 empty] | No Problem
[8 empty] | 2 | Dump Truck For Embt. And Pavement Layers
[8 empty] | 3 | Service Vehecle
[8 empty] | 4 | Jack Hamer For Stone Prodn
Formulas:
Completion = [Total]+[Start]

## Summary (2)
CROSS-LAND Construction
Project:- |  | HARO SABU LELLO QAQE DS6 STANDARD RURAL ROAD PROJECT
Time | Contract time | EOT | Total Contract time | Commencement Date | Completion Date | Elapsed time
| 730 | 300 | 1030 | 2013-08-03 | 2016-05-29 | 789
Cal.Days
ADDELE SEKINA DS6 STANDARD RURAL ROAD PROJECT |  |  |  | PROFIT(A) |  | 1925464.771
|  |  |  | ADAVANCE REPAYMENT (E) | 20% | -636792.898
| Month One |  |  | RETENTION (F) | 5% | -159198.2245
| From | To |  | WITH HOLD (G) | 0% | 0
| 2015-09-01 | 2015-10-01 |  | LOAN REPAYMENT(H) | 0% | 0
|  |  |  | NET CASH INFLOW (J) |  | 2721455.8935
Division | Description | Contract Amount | Previous Amount | This Period Plan Amount | This Period Excuted Amount | IPC Excuted Amount | Todate | Todate. Vs. Contract
BILL NO. 1 | GENERAL PROVISION | 4403495 | 2683500 | 11500 | 11500 | 11500 | 2695000 | 61.2%
BILL NO. 2 | SITE CLEARING | 2625000 | 2148832.84 | 0 | 0 | 0 | 2148832.84 | 81.86%
BILL NO. 3 | MINOR DRAINAGE | 42901535.5 | 5681846.3223 | 0 | 297438 | 353088 | 6034934.3223 | 14.07%
BILL NO. 4 | EARTHWORKS | 144033679.11 | 94263374.8635 | 2064330.189 | 134221.8 | 2797776.49 | 97061151.3535 | 67.39%
BILL NO. 5 | ROAD BASE, SUB BASE, BASE COURSE AND GRAVEL SHOULDER | 11616753.75 | 0 | 0 | 0 | 0 | 0 | 0%
BILL NO. 8 | STRUCTURES | 20817885 | 11283222.2137 | 0 | 0 | 21600 | 11304822.2137 | 54.3%
BILL NO. 9 | ANCILLARY WORKS | 1070200 | 0 | 0 | 0 | 0 | 0 | 0%
TOTAL |  | 227468548.36 | 116060776.2395 | 2075830.189 | 443159.8 | 3183964.49 | 119244740.7295
EXPENSE
DESCREPTION |  |  | Planned | Actual | %age from Income | Remark
Basic Salary (Permanent Employee ) |  |  | 564334.8843 | 312638.06
Allowance Daily(Permanent Employee ) |  |  | 0 | 15150
Per Dime |  |  | 0 | 109160
Overtime (Permanent Employee ) |  |  | 0 | 2964.7404
Pension (Permanent Employee ) |  |  | 0 | 34390.1866
Basic Salary (Daily labor ) |  |  | 0 | 66419
Overtime (Daily labor ) |  |  | 0 | 1317.81
Own Equipment |  |  | 0 | 306107.6667
Rental Equipment |  |  | 0 | 57300
Fuel(Rental) |  |  | 0 | 14527
Fuel(Own) |  |  | 0 | 188351.19
Lubricant (10% of Fuel Cost for Plan) |  |  | 0 | 0
Spare Part (10% of Own Equipment Cost for Plan) |  |  | 0 | 0
Construction Material |  |  | 0 | 35765
Others |  |  | 0 | 0
Overhead Cost (10% of total) |  |  | 56433.4884 | 114409.0654
TOTAL |  |  | 620768.3728 | 1258499.719
Formulas:
Completion Date = [Total Contract time]+[Commencement Date]
EOT = [Contract time]+30

## BOQ Rev
Haro Sabu-Lelo-Qaqe DS6 rural road
Remaining Quantity And Amount (Draft)
Bill Item No. | Description | Unit | Rate | Quantity | [9 empty] | Amount |  |  |  |  | 791224.66 | 673917.34 | 1465142 | 128932496
|  |  |  | As per contrcat (BOQ) | As per original contract design | As per contractor revision and approved drawing | As per Final Revision | Remaining Quantity | September Plan | September Excuted | September Plan Amount | September Excuted Amount | Percent Accomplishment (Plan Vs Excuted) | October Plan | As per original contract design | As per contractor revision and approved | As per Final Revision | Remaining | 33575.01 | 26748.73 | 60323.74
1000 | Bill No.1 GENERAL PROVISION SUM
(i) | House for Senior staff | m2 | 5000 | 30 | 30 | 30 | 30 | 30 |  |  | 0 | 0 | - |  | 150000 | 150000 | 150000 | 150000
(ii) | Type "A" acommodation to be provided for senior staff | LS | 50000 | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | - |  | 50000 | 50000 | 50000 | 50000
(iii) | House for Junior staff | m2 | 5000 | 25 | 25 | 25 | 25 |  |  |  | 0 | 0 | - |  | 125000 | 125000 | 125000 | 0
(iv) | Type "B" acommodation to be provided for senior staff | LS | 50000 | 1 | 1 | 1 | 1 |  |  |  | 0 | 0 | - |  | 50000 | 50000 | 50000 | 0 | 30847.63 | 25625.27
2 | Office Accommodation for Engineers | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 | 64422.64 | 52374
(i) | Engineers Employer Counterparts office Accommodation | LS | 50000 | 1 | 1 | 1 | 1 |  |  |  | 0 | 0 | - |  | 50000 | 50000 | 50000 | 0
(ii) | Office builing for Engineers staff | m2 | 5000 | 20 | 20 | 20 | 20 |  |  |  | 0 | 0 | - |  | 100000 | 100000 | 100000 | 0
3 | Laboratory building and equpments Office Accommodation | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(i) | Laboratory building | m2 | 2500 | 60 | 60 | 60 | 60 |  |  |  | 0 | 0 | - |  | 150000 | 150000 | 150000 | 0
(ii) | Provision of Laboratory equpments for Gravel Road | LS | 600000 | 1 | 1 | 1 | 1 |  |  |  | 0 | 0 | - |  | 600000 | 600000 | 600000 | 0
(iii) | Maintenance of Laboratory building and equpments for | month | 1000 | 33 | 33 | 33 | 33 |  |  |  | 0 | 0 | - |  | 33000 | 33000 | 33000 | 0
4 | Provision of Surveying equpments including Maintenance | LS | 400000 | 1 | 1 | 1 | 1 |  |  |  | 0 | 0 | - |  | 400000 | 400000 | 400000 | 0
5 | Additional Office and laboratory equipment ordered by the Engineer | LS | 100000 | 1 | 1 | 1 | 1 |  |  |  | 0 | 0 | - |  | 100000 | 100000 | 100000 | 0
6 | Provision of Computer with printer & UPS | LS | 20000 | 3 | 3 | 3 | 3 |  |  |  | 0 | 0 | - |  | 60000 | 60000 | 60000 | 0
7 | Mobile charge for Engineerwith all accessories including 500 birrcharge per monthly for resident Engineer | No | 10000 | 3 | 3 | 3 | 3 |  | 0.15 | 0.15 | 1500 | 1500 | 100% | 1500 | 30000 | 30000 | 30000 | 0
8 | Vehicular Provision to the Engineers (counter & consultant) including fueland maintenance | No | 2000000 | 1 | 1 | 1 | 1 |  |  |  | 0 | 0 | - |  | 2000000 | 2000000 | 2000000 | 0
8(a) | Fuel, service maintain ad insurance, for vehicle type "A" , based on average 3000 km/month/vehicle | Veh-month | 10000 | 45 | 45 | 45 | 45 |  | 1 | 1 | 10000 | 10000 | 100% | 10000 | 450000 | 450000 | 450000 | 0
9 | Survey equipment as per 1403 (g) and 1409 (E) | No | 10 | 45 | 45 | 45 | 45 |  |  |  | 0 | 0 | - |  | 450 | 450 | 450 | 0
9(a) | Provide Survey equipment with all accessories | Km | 1 | 25000 | 25000 | 25000 | 25000 |  |  |  | 0 | 0 | - |  | 25000 | 25000 | 25000 | 0
9(b) | Provision of service and maintenance for all equipment | Veh-month | 1 | 45 | 45 | 45 | 45 |  |  |  | 0 | 0 | - |  | 45 | 45 | 45 | 0
| Laboratory testing (additional testing to be carried out at external (commercial)) | LS | 10000 | 3 | 3 | 3 | 3 |  |  |  | 0 | 0 | - |  | 30000 | 30000 | 30000 | 0
| Carried Forward to Bill Summary | [9 empty] | 11500 | 11500 | 100% | 11500 | 4403495 | 4403495 | 4403495 | 200000
2000 | Bill No.2 SITE CLEARANCE | [11 empty] | -
21.01 | Clearing & grubing | ha | 35000 | 75 | 54.15 | 75 | 75 | 27.65 |  |  | 0 | 0 | - |  | 1895250 | 2625000 | 2625000 | 967750
| Carried Forward to Bill Summary | [9 empty] | 0 | 0 | - | 0 | 1895250 | 2625000 | 2625000 | 967750
3000 | Bill N0.3 DRAINAGE | [9 empty] | 0 | 0 | -
31.01 | Excavation of open drain (Channel Excavation) | [9 empty] | 0 | 0 | - |  |  |  |  | 0
31.01(a) | Soft material at any depth/with irrespective of depth | m3 | 75 | 18960 | 1103.75 | 13702 | 13702 |  |  |  | 0 | 0 | - |  | 82781.25 | 1027650 | 1027650 | 0
31.01(b) | Intermediate material at any depth/with irrespective of depth | m3 | 80 | 7865 |  | 1612 | 1612 |  |  |  | 0 | 0 | - |  | 0 | 128960 | 128960 | 0 |  | 58.98
31.01(c) | Hard material at any depth/with irrespective of depth | m3 | 115 | 1865 |  | 806 | 806 |  |  |  | 0 | 0 | - |  | 0 | 92690 | 92690 | 0
|  | m3 |  | 0 | [6 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
32.01 | STRUCTURAL EXCAVATION | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
32.01(a) | Excavation in Soft materialat any depth | m3 | 75 | 3476 | 8681.83 | 7500 | 7500 | 4504.05 |  |  | 0 | 0 | - |  | 651137.25 | 562500 | 562500 | 337803.75
32.01(b) | Excavation in Intermediate materialat any depth | m3 | 80 | 2165 | 0 | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
32.01(c) | Excavation in hard materialat any depth | m3 | 115 | 986 | 868.18 | 1209 | 1209 |  |  |  | 0 | 0 | - |  | 99840.7 | 139035 | 139035 | 0
3200 | Culverts and appurtenant structures | [9 empty] | 0 | 0 | - |  | 0 |  |  | 0
32.01(a) | Excavating soft material irrespective of depth | [9 empty] | 0 | 0 | - |  | 0 |  |  | 0
32.01(a)(i) | Culverts | m3 | 250 | 0 | [6 empty] | 0 | 0 | - | 0 | 0 | 0 | 0 | 0
32.1(a)(ii) | Retaining wall | m3 | 250 | 0 | [6 empty] | 0 | 0 | - | 0 | 0 | 0 | 0 | 0
32.02(b) | Backfilling using imported selected materials for | [9 empty] | 0 | 0 | - |  | 0 |  |  | 0
32.02(b)(i) | Culverts |  | 125 | 2488 |  | 3557.5 | 3557.5 | 3246.42 |  | 120 | 0 | 15000 | - |  | 0 | 444687.5 | 444687.5 | 405802.5
32.01(b)(ii) | Retaining wall |  | 125 | 640 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0 | 3925.18
32.02(b) | Backfilling | [9 empty] | 0 | 0 | - |  | 0 |  |  | 0
32.02 (a) | Using excavated material |  | 100 | 512 | 602.8 | 512 | 512 | 678.76 |  |  | 0 | 0 | - |  | 60280 | 51200 | 51200 | 67876
32.02(b) | Using imported material for |  | 125 | 2420 | 4446.02 | 0 | 0 |  |  |  | 0 | 0 | - |  | 555752.5 | 0 | 0 | 0
32.03 | Concrete Pipe Culverts | [9 empty] | 0 | 0 | - |  | 0 |  |  | 0
32.03(i)(a) | 36" diameter R. C. pipe on class "A" bedding | LM | 5000 | 0 | [6 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
32.03(i)(b) | 36" diameter R. C. pipe on class "B" bedding | LM | 4800 | 320 | 324 | 300 | 300 | 169 |  |  | 0 | 0 | - |  | 1555200 | 1440000 | 1440000 | 811200
32.03(i)(c) | 36" diameter R. C. pipe on class "C" bedding | LM | 4500 | [7 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
32.03(ii)(a) | 42" diameter R. C. pipe on class "B" bedding | LM | 5500 | 0 | [6 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
32.03(ii)(b) | 42" diameter R. C. pipe on class "B" bedding | LM | 5400 | 160 | 34 | 24 | 24 | 24 |  |  | 0 | 0 | - |  | 183600 | 129600 | 129600 | 129600
32.03(ii)(c) | 42" diameter R. C. pipe on class "B" bedding | LM | 5000 | 0 | [6 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
32.03(iii) | 48" diameter R. C. pipe on class "B" bedding | LM | 6000 | 240 | 249 | 182 | 182 | 122 |  |  | 0 | 0 | - |  | 1494000 | 1092000 | 1092000 | 732000
32.07 | Cast-In-situ Concrete and Formwork (Grade 25/20) | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 4241.83 | 2180.74
32.07(a)i | Class A concrete for Culverts (box/slab), inlet and outlet structures and skewed ends including formwork, false work, joints and class U2 surface finish | m3 | 4900 | 60 | 58.08 | 441.33 | 441.33 | 347.57 |  |  | 0 | 0 | - | 449722 | 284592 | 2162517 | 2162517 | 1703093 | 423.89 | 2355.97 | 6651.7
32.07(b)ii | Class C(20/20) concrete including formwork | m3 | 4700 | 245 | 574.08 | 145 | 145 | 32.7643 |  |  | 0 | 0 | - |  | 2698176 | 681500 | 681500 | 153992.398 |  | 6357.08
32.1 | Steel Reinforcement | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 2551.35
32.10(b) | High tensile steel | ton | 49000 | 9.8 | 22.58 | 45.9 | 45.9 | 37.031 |  |  | 0 | 0 | - | 462070 | 1106420 | 2249100 | 2249100 | 1814520.47 | 347.57 | 3403.58
32.10(b) | High tensile steel in Culverts | ton | 49000 | 1.2 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0 | 32.7643 | 5942
33.01(i) | (17*45)cm concrete curb or 15*25 cm concrete curb in town section at located & directed by engineer whosever appropriate | LM | 600 | 680 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 1087.2
34 | Pitching, stone work and erosion protection | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 6778.72
34.01 | Grouted stone ditching | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 4313.3
34.01(b)i | Grouted rubble paved waterway (pipe) | m2 | 300 | 982 | 1787 | 1601.34 | 1601.34 | 1214.159 |  |  | 0 | 0 | - | 1860480 | 536100 | 480402 | 480402 | 364247.7 | 52662.7008 | 37031.03
34.01(b)ii | Grouted paved waterway (paved ditch) | m2 | 300 | 8125 | 16512 | 73142.64 | 73142.64 | 73142.64 |  | 941.46 | 0 | 282438 | - |  | 4953600 | 21942792 | 21942792 | 21942792
34.01(b)iii | Type 'B' paved waterway | m2 | 300 | 650 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
34.01(b)iv | Type 'C' paved waterway | m2 | 300 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
34.02 | Hand Laid Rock embankment for retaining wall | m3 | 200 | 86 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 1431698.4
34.03 | Stone Masonry Walls | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 2640000
34.03(b)i | Cemented mortared stone wall | m3 | 1800 | 0 | 8972.88 | 4146.39 | 4146.39 | 2152.17 |  |  | 0 | 0 | - |  | 16151184 | 7463502 | 7463502 | 3873906 | 778.8
34.03(b)i | Pipe endwall | m3 | 1800 | 6784 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
34.03(b)ii | Retainingwall | m3 | 1800 | 3126 |  | 1563 | 1563 |  |  |  | 0 | 0 | - |  | 0 | 2813400 | 2813400 | 0 |  | 359832
36.06 | Excavation for foundation trenchs during | [9 empty] | 0 | 0 | - |  | 0 |  |  | 0 | 2152.17 | 5880
| Masonry work (retainingwall) | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 117070.8
(a)i | In all classes of material | m3 | 75 | 786 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
(b)ii | In solid rock (retainingwall) | m3 | 15 | 420 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
| Carried Forward to Bill Summary | [9 empty] | 0 | 297438 | - | 2772272 | 30412663.7 | 42901535.5 | 42901535.5 | 32336833.818
4000 | Bill No.4 EARTH WORKS | [10 empty] | 0 | - |  | 0 |  |  | 0 | latest Ipc | 44.7
4100 | Preparation of roadbed | [10 empty] | 0 | - |  | 0 |  |  | 0
41.03 | Roadbed preparation and compactiong of material | [10 empty] | 0 | - |  | 0 |  |  | 0
a) | Compaction of modified AASHTO density | m3 | 20 | 72000 | 64980 | 72000 | 72000 |  |  | 240 | 0 | 4800 | - |  | 1299600 | 1440000 | 1440000 | 0 | 11241.2714
4200 | Road way and borrow materials | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 | 1470613.93
42.01 | Fill with unlimited hauling distance compacted to 200mm to 83% of modified AASHTO | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 | 218514.28
42.01 (a) (ii)A | Cut to Fill embankment compacted in 200mm layer to 100% modified AASHTO density with CBR min .to be 4% | m3 | 89 | 770000 | 617759.68 | 221338.73 | 218760.55 | 210957.288 |  | 2029.8 | 0 | 2029.8 | - | 21288.08 | 54980611.52 | 19699146.97 | 19469688.95 | 18775198.632 |  |  |  |  | 1173786.636
42.01a(ii)B | Borrow to fill compacted in 200 mm layers to 100% modified AASHTO density (max. dry density) | m3 | 125 | 186452 | 0 | 100 | 100 |  |  |  | 0 | 0 | - |  | 0 | 12500 | 12500 | 0 | 1946.908 | 52388.91
42.01 (a) | Rockfill | m3 | 250 | 1886 | 1000 | 1886 |  |  |  |  | 0 | 0 | - |  | 250000 | 471500 | 0 | 0 | 0 | 62808.71 |  |  | 127928.09
42.01 (b) | Capping layerwhere needed | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 | 0
b(i) | G15/20 | m3 | 117 | 18564 | 47443.03 | 52684.89 | 52684.56 | 52388.91 |  | 400 | 0 | 46800 | - | 1061642.79 | 5550834.51 | 6164132.13 | 6164093.52 | 6129502.47 | 0 |  |  |  | 169649.4
b(ii) | G7 | m3 | 115 | 4876 | 53512.87 | 70332.72 | 70332.72 | 62808.71 |  | 700.8 | 0 | 80592 | - | 870182 | 6153980.05 | 8088262.8 | 8088262.8 | 7223001.65 | 2839.4
42.03 | Cut to Spoil material to unlimited hauling distance obtained from | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 551899.2474
42.03(a) | Extra over item 42.01 for Common (normal) excavation to spoil | m3 | 88 | 68956 | 1475969.1 | 801684.5011 | 899282.62 | 833846.7672 |  |  | 0 | 0 | - | 8913746.05 | 129885280.8 | 70548236.0968 | 79136870.56 | 73378515.5112 | 634626.3067
42.03(b) | Extra over item 42.01 for Intermediate materials excavation to spoil | m3 | 99 | 28986 | 40367 | 339696.8225 | 127177.69 |  | 3910.331 |  | 387122.769 | 0 | 0% |  | 3996333 | 33629985.4275 | 12590591.31 | 0 | 0 | 193873003.87
42.03(c) | Extra over item 42.01 for excavating and breaking in Rock (Hard material) excavation to spoil | m3 | 119 | 18452 | 22043.89 | 217405.9664 | 143963.63 |  | 14094.18 |  | 1677207.42 | 0 | 0% |  | 2623222.91 | 25871310.0016 | 17131671.97 | 0 | 29518.03 | 118924.4713
| Carried Forward to Bill Summary | [9 empty] | 2064330.189 | 134221.8 | 6.502% | 10866858.92 | 204739862.79 | 165925073.4259 | 144033679.11 | 105506218.2632
5000 | Bill No 5 : ROAD BASE SUBBASE BASE COURSE AND GRAVEL SHOULDER | [10 empty] | 0 | - |  | 0 |  |  |  | 1173786.64
54.01(A)* | Gravel wearing course to be used to construct the carriageway and shoulder compacted to 85% of modified AASHTO density CBR >20 after 4 days of soaking | m3 | 175 | 80850 | 61011.39 | 66381.45 | 66381.45 | 66381.45 |  |  | 0 | 0 | - |  | 10676993.25 | 11616753.75 | 11616753.75 | 11616753.75
| Carried Forward to Bill Summary | [5 empty] | 66381.45 |  |  |  | 0 | 0 | - | 0 | 10676993.25 | 11616753.75 | 11616753.75 | 11616753.75
8000 | Bill No.8 STRUCTURES (12m,8m and 8m) | [10 empty] | 0 | - |  | 0
8100 | Foundation for Structures | [10 empty] | 0 | - |  | 0 |  |  | 0
81.01 | Foundation Investigation | [10 empty] | 0 | - |  | 0 |  |  | 0
81.01(a) | Additional Foundation Investigation | PS |  |  | 2000000 | [5 empty] | 0 | 0 | - |  | 0 | 200000 | 200000 | 0
81.01(b) | Allowed % for overhead and profit on 81.01(a) | % | 0.35 | [7 empty] | 0 | 0 | - |  | 0 | 70000 | 70000 | 0
81.02 | Excavation of materials | [9 empty] | 0 | 0 | - |  | 0 |  |  | 0
(a)i | Excavation of soft material irrespective of depth | m3 | 135 | 2654 | 3668.15 | 3880 | 3880 | 3844.5 |  |  | 0 | 0 | - |  | 495200.25 | 523800 | 523800 | 519007.5
(a)i | Excavation of intermediate material irrespective of depth | m3 | 200 | 1580 | 0 | 1458.94 | 1458.94 |  |  |  | 0 | 0 | - |  | 0 | 291788 | 291788 | 0
(b)ii | Excavation of hard (rock) material irrespective of depth | m3 | 500 | 865 | 3308.36 | 1832.3 | 1832.3 | 786 |  |  | 0 | 0 | - |  | 1654180 | 916150 | 916150 | 393000
[11 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
81.05 | Backfilling to Excavation Utilizing | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(a) | material from excavation/backfilling with good selected materia from excavated well compacted in layers not exceeding 20 cm thickness | m3 | 120 | 786 | 199.81 | 0 | 0 |  |  |  | 0 | 0 | - |  | 23977.2 | 0 | 0 | 0
(b) | Imported material | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(i) | Selected granular material | m3 | 190 | 1865 | 2604.57 | 2478.4 | 2478.4 | 1393.8 |  |  | 0 | 0 | - |  | 494868.3 | 470896 | 470896 | 264822
(ii) | Hand-laid Rockfill/Hand-laid Rock embankement | m3 | 300 | 568 | 1177.09 | 1877.6 | 1877.6 | 1156 |  |  | 0 | 0 | - |  | 353127 | 563280 | 563280 | 346800
(iii) | Stone pitching | m3 | 300 | 422 |  | 422 | 422 | 422 |  |  | 0 | 0 | - |  | 0 | 126600 | 126600 | 126600
(iv) | Hand-laid Rock riprap | m3 | 200 | 344 | 742.41 | 344 | 344 | 344 |  |  | 0 | 0 | - |  | 148482 | 68800 | 68800 | 68800
82.01 | Formworks | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(a) | Formworks to provide class F1 finishes | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(i) | Concrete footing of abutments and wingwalls | m2 | 1000 | 164 |  | 260.36 | 260.36 | 173.5733 |  |  | 0 | 0 | - |  | 0 | 260360 | 260360 | 173573.3333
(ii) | Footing of piers | m2 | 1000 | 122 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
(iii) | Soffit of concrete deck slab | m2 | 1000 | 687 |  | 476.36 | 476.36 | 476.36 |  |  | 0 | 0 | - |  | 0 | 476360 | 476360 | 476360
(iv) | To invisible parts of R.C abutments and wingwalls | m2 | 1000 | 145 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
(b) | Formworks to provide class F2 finishes | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(i) | To sidewalks in main slab and visible part of girder | m2 | 1000 | 126 |  | 753.66 | 753.66 | 753.66 |  |  | 0 | 0 | - |  | 0 | 753660 | 753660 | 753660
(ii) | To invisible parts of piers | m2 | 1000 | 224 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
(iii) | To visible parts of abutments and wingwalls | m2 | 1000 | 262 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
(iv) | To cross girders | m2 | 1000 | 140 |  | 59 | 59 | 59 |  |  | 0 | 0 | - |  | 0 | 59000 | 59000 | 59000
83.01 | Steel Reinforcement | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(a) | Mild steel bars (Grade 300) | Ton | 49000 | 24 | 42.1 | 24.73 | 24.73 | 24.73 |  |  | 0 | 0 | - | 475006 | 2062900 | 1211770 | 1211770 | 1211770
(b) | High yield stress steel bars (Grade 420) | Ton | 49000 | 28 | 24.39 | 33.13 | 33.13 | 33.13 |  |  | 0 | 0 | - |  | 1195110 | 1623370 | 1623370 | 1623370
84 | Concrete For Structures | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
84.01 | Cast in Situ Concrete | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
a | Class A Concrete class C-30 in all part of super structure ,walkways and indicated on drawing and directed by the engineer | m3 | 5000 | 168 | 713.73 | 759.16 | 759.16 | 759.16 |  |  | 0 | 0 | - | 372091.3 | 3568650 | 3795800 | 3795800 | 3795800
b | Ditto but class C-25 on the seat ofgirder and as Rc of WWS and abutments as indicated on the drawing or directed by the engineer | m3 | 4900 | 45 |  | 26.49 | 26.49 | 17.66 |  |  | 0 | 0 | - |  | 0 | 129801 | 129801 | 86534
c | Class C-20 as indicated on the drawings and directed by the engineer | m3 | 4800 | 360 | 193.32 | 154.8 | 154.8 | 103.2 |  |  | 0 | 0 | - |  | 927936 | 743040 | 743040 | 495360
d | Class C-15 lean concerete under footings of pipers as per the drawing | m3 | 4000 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
d | Class C-5 lean concerete under footings of abutments and WWs as per the drawing | m3 | 3800 | 22 |  | 94.3 | 94.3 | 62.8667 |  |  | 0 | 0 | - |  | 0 | 358340 | 358340 | 238893.3333
87.039a) | Elastomeric bearing | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
9i) | Type - 1 | pc | 30000 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | - | 0 | 0 | 0 | 0 | 0
9ii) | Type - 20[0.67*0.4*0.4] | pc | 30000 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | - | 0 | 0 | 0 | 0 | 0
(b) | Plate bearing [0.45*0.35*0.05] | pc | 30000 | 12 | 16 | 16 | 16 | 16 |  |  | 0 | 0 | - |  | 480000 | 480000 | 480000 | 480000
87.07 | Steel metal pipe bridge railling/post of 80mm and 60mm respectively | lm | 500 | 240 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
87.07(b) | Concrete parapets and railings | lm | 500 | 64 | 135.35 | 135 | 135 | 135 |  |  | 0 | 0 | - |  | 67675 | 67500 | 67500 | 67500
87.19(a) | Drainage pipes and weep holes | No. | 200 | 240 |  | 60 | 60 | 60 |  |  | 0 | 0 | - |  | 0 | 12000 | 12000 | 12000
87.13 | Expansion joints | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(a) | Expansion joint including 20mm compressible joint filler board | lm | 100 | 116.4 | 116.4 | 116.4 | 116.4 | 116.4 |  |  | 0 | 0 | - |  | 11640 | 11640 | 11640 | 11640
87.16 | Sealing joints with | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(a) | Joint sealant, 20mm deep grouted poly sulphide sealant | lm | 100 | 116.4 | 116.4 | 116.4 | 116.4 | 116.4 |  |  | 0 | 0 | - |  | 11640 | 11640 | 11640 | 11640
89.01 | Stone masonry | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(a) | Cement-mortared stone masonry walls (class "B" masonry) | m3 | 1800 | 2956 | 3777.94 | 3633.4 | 3633.4 | 2335.5 |  |  | 0 | 0 | - |  | 6800292 | 6540120 | 6540120 | 4203900
(b) | Pointing of both abutment and WWs with 1:4 mortar | m2 | 100 | 642 |  | 1872 | 1872 | 1872 |  |  | 0 | 0 | - |  | 0 | 187200 | 187200 | 187200
91.01 | Cut of wall construction madeof stone masonry along river bank on both U/S and D/S | m3 | 1800 | 185 |  | 185 | 185 | 185 |  |  | 0 | 0 | - |  | 0 | 333000 | 333000 | 333000
9100 | Gabion construction 1m*1m*1m | [9 empty] | 0 | 0 | - |  | 0 |  |  | 0 |  | 3541.54
91.01 | Foundation trench excavation and back filling in all class of material other than rock | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0 |  | 91.86
a | Excavation for foundation trenches | m3 | 135 | 156 | 220.5 | 156 | 156 | 156 |  |  | 0 | 0 | - |  | 29767.5 | 21060 | 21060 | 21060 |  | 165348
b | Back filling | m3 | 190 | 34 | 22.58 | 34 | 34 | 34 |  |  | 0 | 0 | - |  | 4290.2 | 6460 | 6460 | 6460
91.03 | Gabion | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
a | Galvanized gabion boxes, 80*100 mesh size 1m*1m*1m | m3 | 1300 | 356 | 294 | 356 | 356 | 356 |  |  | 0 | 0 | - |  | 382200 | 462800 | 462800 | 462800
91.04 | Folter fabric (Geotextile) | m2 | 119 | 350 | 336 | 350 | 350 | 350 |  |  | 0 | 0 | - |  | 39984 | 41650 | 41650 | 41650
| Carried Forward to Bill Summary | [9 empty] | 0 | 0 | - | 847097.3 | 18751919.45 | 20817885 | 20817885 | 16472200.1667
9000 | Bill No.9 ANCILLARY WORKS | [11 empty] | - |  | 0
| Delineation, Markers and Kilometer Posts | [11 empty] | - |  | 0
92.01(a) | Delineator posts/guidepost | No | 300 | 2560 | 2691 | 2560 | 2560 | 2560 |  |  | 0 | 0 | - |  | 807300 | 768000 | 768000 | 768000
92.01(c) | Kilometer posts | No | 500 | 36 |  | 36 | 36 | 36 |  |  | 0 | 0 | - |  | 0 | 18000 | 18000 | 18000
94.01 | Sign post and Faces | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
(a) | Sign faces made by Aluminum alloy of thickness 2mm and area not exceeding 2m2 | m2 | 1000 | 22 | 5.28 | 22 | 22 | 22 |  |  | 0 | 0 | - |  | 5280 | 22000 | 22000 | 22000
(b) | Ditto but area exceeding 2sqm but not exceeding 10 sqm | m2 | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | - |  | 0 | 0 | 0 | 0
94.02 | Sign supports: | [9 empty] | 0 | 0 | - |  | 0 | 0 | 0 | 0
94.02(a) | Class A (as per the drawing) Concrete Sign Support | No | 3800 | 69 | 66 | 69 | 69 | 69 |  |  | 0 | 0 | - |  | 250800 | 262200 | 262200 | 262200
94.03 | Class C concrete in road sign footing including excavation and backfilling | m3 |  | 2.6 | 1.24 | 2.6 | 2.6 | 2.6 |  |  | 0 | 0 | - | 0 | 0 | 0 | 0 | 0
| Carried Forward to Bill Summary | [9 empty] | 0 | 0 | - | 0 | 1063380 | 1070200 | 1070200 | 1070200
| Total | [9 empty] | 2075830.189 | 443159.8 | 21.35% | 14497728.22 | 271943564.19 | 249359942.6759 | 227468548.36 | 168169955.9979
[17 empty] | 10.8 | 71615785.9627
1.18
38.3333
[8 empty] | 15.7895 | [5 empty] | 1.5
10.4167
v

## D M S
Cross-land Construction Company
Project: Haro sebu-Lelo-Qaqe
Macheneries List
No | TYPE | PLAT No. | MODEL | Status | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Tursday | Week 32 | Fuel | UN cons
DOZER
1 | Dozer | 9EM 08520 | CAT D8R | O | 17.33 | 16.75 | 0 | 18.67 | 8 | 12.5 | 11 | 84.25 | 2060 | 24.451
|  |  |  | I | 0.33 | 2.08 | 0 | 0 | 12 | 7.5 | 9 | 30.91 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0.33 |  | 0
2 | Dozer | D8R 08518 | CAT D8R | O | 10.83 | 12 | 0 | 11.33 | 7.83 | 4.92 | 12.33 | 59.24 | 2500 | 42.2012
|  |  |  | I | 0.17 | 0.33 | 0 | 0 | 5.17 | 8.08 | 0.17 | 13.92 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
3 | Dozer | D8R 03152 | CAT D8R | O | 18 | 16.83 | 0 | 20 | 8 | 12.66 | 11.5 | 86.99 | 2500 | 28.7389
|  |  |  | I | 0.5 | 1.5 | 0 | 0 | 12 | 7.33 | 8.5 | 29.83 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
GRADER |  |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | #REF!
1 | Grader | 0498 | XG 31802 | O | 7.5 | 9.5 | 0 | 9.4 | 5.3 | 6.5 | 9.63 | 47.83 | 310 | 6.4813
|  |  |  | I | 2.5 | 0.5 | 0 | 0 | 4.7 | 3.5 | 0 | 11.2 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
2 | Grader | #REF! | 140H | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
2 | Grader |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
7 | Grader |  | 140H | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | #DIV/0!
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
ROLLER |  |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | #REF!
1 | Roller | 0166 | XGMA | O | 3.42 | 2 | 0 | 1.5 | 2.5 | 0 | 3.08 | 12.5 | 270 | 21.6
|  |  |  | I | 4.58 | 6 | 0 | 6.5 | 5.5 | 8 | 4.92 | 35.5 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
2 | Roller | 0167 | XGMA | O | 2.5 | 3.5 | 0 | 6.5 | 7.33 | 0 | 2 | 21.83 | 270 | 12.3683
|  |  |  | I | 5.5 | 4.5 | 0 | 1.5 | 0 | 8 | 6 | 25.5 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
2 | Smooth roller rental | #REF! |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
LOADER |  |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #DIV/0!
1 | Loader | 0152 | XG953H | O | 9.83 | 13.67 | 0 | 10 | 5.17 | 0 | 10.2 | 48.87 |  | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 4.83 | 10 | 0 | 14.83 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
2 |  | 0300 | XG953H | O | 0 | 0.25 | 0 | 10 | 8 | 7 | 0.5 | 25.75
| Loader |  |  | I | 10 | 9.75 | 0 | 0 | 2 | 3 | 9.5 | 34.25
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Loader | 148 | XG953H | O | 9.7 | 12.9 | 0 | 12.6 | 6 | 0 | 0 | 41.2
|  |  |  | I | 0 | 0 | 0 | 0 | 4 | 10 | 10 | 24
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Loader | new | XG953H | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EXCAVATOR |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
1 | Excavator(DOSSAN) |  | DX-340 | O | 8.3 | 8.2 | 0 | 8.7 | 4.2 | 0 | 9.1 | 38.5 | 1030 | 26.7532
|  |  |  | I | 0 | 0 | 0 | 0 | 5.8 | 10 | 0 | 15.8 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
2 | Excavator(chain) | N6LA4888 | E385 | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crusher | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #DIV/0!
1 | Crusher | XXX-06-20500153 | 495AG | O | 0 | 6 | 0 | 6.5 | 6.5 | 6.5 | 7 | 32.5 |  | 0
|  |  |  | I | 10 | 3 | 0 | 3.5 | 2.5 | 2.5 | 3 | 24.5 |  | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
3 | crusher Electrical |  |  | O | 0 |  |  | 0 |  |  |  | 0 | 23 | #DIV/0!
|  |  |  | I | 0 |  |  | 0 |  |  |  | 0 |  | #DIV/0!
|  |  |  | D | 0 |  |  | 0 |  |  |  | 0 |  | #DIV/0!
MIXER | [13 empty] | #DIV/0!
1 | MIXER LOMBARDINI | 1DK/M486 | 15D3505.360 | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
2 | MIXER LOMBARDINI |  | 5750 HOPPER | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
3 | MIXER |  |  | O | 0 |  |  | 0 |  |  | 0 | 0
|  |  |  | I | 0 |  |  | 0 |  |  | 0 | 0
|  |  |  | D | 0 |  |  | 0 |  |  | 0 | 0
4 | MIXER |  |  | O | 0 |  |  | 0 |  |  | 0 | 0 |  | #DIV/0!
|  |  |  | I | 0 |  |  | 0 |  |  | 0 | 0 |  | #DIV/0!
|  |  |  | D | 0 |  |  | 0 |  |  | 0 | 0 |  | #DIV/0!
4 | MIXER |  |  | O | 0 |  |  | 0 |  |  | 0 | 0 |  | #DIV/0!
|  |  |  | I | 0 |  |  | 0 |  |  | 0 | 0 |  | #DIV/0!
|  |  |  | D | 0 |  |  | 0 |  |  | 0 | 0 |  | #DIV/0!
VIBRATOR | [11 empty] | 0 |  | #DIV/0!
1 | Vibrator (Rubin) | A | EY.20C | O | [7 empty] | 0 |  | #DIV/0!
|  |  |  | I | [7 empty] | 0 |  | #DIV/0!
|  |  |  | D | [7 empty] | 0 |  | #DIV/0!
2 | Vibrator (Rubin) | B | EY.20C | O | [7 empty] | 0 |  | #DIV/0!
|  |  |  | I | [7 empty] | 0 |  | #DIV/0!
|  |  |  | D | [7 empty] | 0 |  | #DIV/0!
3 | Vibrator (Rubin) (new) | C | EY.20C | O | [7 empty] | 0 |  | #DIV/0!
|  |  |  | I | [7 empty] | 0 |  | #DIV/0!
|  |  |  | D | [7 empty] | 0 |  | #DIV/0!
4 | Vibrator Petrol | 6686919 | EY.20D | O | [7 empty] | 0 |  | #DIV/0!
|  |  |  | I | [7 empty] | 0 |  | #DIV/0!
|  |  |  | D | [7 empty] | 0 |  | #DIV/0!
5 | Vibrator Petrol |  |  | O | [7 empty] | 0 |  | #DIV/0!
|  |  |  | I | [7 empty] | 0 |  | #DIV/0!
|  |  |  | D | [7 empty] | 0 |  | #DIV/0!
6 | Vibrator Petrol |  |  | O | [7 empty] | 0 |  | #DIV/0!
|  |  |  | I | [7 empty] | 0 |  | #DIV/0!
|  |  |  | D | [7 empty] | 0 |  | #DIV/0!
1 |  |  | Z.O.28EU | O | [7 empty] | 0
| Air compressor |  |  | I | [7 empty] | 0
|  |  |  | D | [7 empty] | 0
WATER AND FUEL PUMP
1 | Dissel Water Pump unoperational | Km 186 F(A) | d120302061 | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Km 186 F(A) | KAMA | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Benzine Water Pump | G200 | Eagle | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | FUEL Pump | RTSOZB26-36Q | OHV | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Water Pump |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Water Pump |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DUMP TRUCK
1 | water truck | #REF! | UD | O
I
D
1 | Dump truck (Genlyon) | 3-ET-61220 | Genlyon 380 | O | 10 | 10 | 0 | 10 | 8 | 6 | 10 | 54
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Small Dump Truck (Nissan) | 3-ET-10467 | Nissan | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 48
3 | Dump truck | 3-ET-70117 | SINOTRUCK | O | 10 | 10 | 0 | 10 | 8 | 0 | 10 | 48
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Dump truck | 3-ET-57870 | SINOTRUCK | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Loader | 10233 | xgma | O | 10 | 10.17 | 0 | 10 | 5.4 | 0 | 9.92 | 45.49
7.3 |  |  |  | I | 0 | 0.17 | 0 | 0 | 0 | 0 | 0.1 | 0.27
7.3333 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Dump truck rental | 3-69520 | SINOTRUCK | O | 8.67 | 11.83 | 0 | 9.87 | 5.8 | 6 | 9.83 | 52
7.4 |  |  |  | I | 0.47 | 0.57 | 0 | 0.3 | 0 | 0 | 0 | 1.34
7.4333 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Dump Truck rental | 3-69538 | SINOTRUCK | O | 9.27 | 10.07 | 0 | 9.62 | 5.33 | 0 | 10 | 44.29
|  |  |  | I | 0 | 0 | 0 | 0.72 | 0 | 0 | 0 | 0.72
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dump truck rental | 3-58699 | SINOTRUCK | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dump truck rental | 3-67361 | SINOTRUCK | O | 8.77 | 11.43 | 0 | 9.75 | 5.83 | 0 | 8.89 | 44.67
|  |  |  | I | 0.47 | 1.2 | 0 | 0.5 | 0 | 0 | 0.96 | 3.13
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dump truck rental | 3-67362 | SINOTRUCK | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dump truck rental | 3-62628 | SINOTRUCK | O | 8.8 | 9.83 | 0 | 12.55 | 5.25 | 0 | 8.48 | 44.91
|  |  |  | I | 1.02 | 0 | 0 | 0 | 0 | 0 | 1.37 | 2.39
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dump truck rental | 3-62629 | SINOTRUCK | O | 8.55 | 12.13 | 0 | 12.12 | 5.13 | 6 | 10 | 53.93
|  |  |  | I | 0.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Dozer | 0800 | CAT D8R | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BackLoader | 3613 | JCB | O | 8 | 10 | 0 | 10 | 10 | 9 | 8 | 55
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dump truck rental | 3-36811 | NISSAN | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Grader | 1152 | Komatsu | O | 6 | 10.67 | 0 | 10 | 6.5 | 0 | 9.17 | 42.34
|  |  |  | I | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Dump truck | 65860 | SINOTRUCK | O | 10 | 10 | 0 | 10 | 10 | 0 | 10 | 50
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Dump truck | 65861 | SINOTRUCK | O | 10 | 10 | 0 | 10 | 10 | 0 | 10 | 50
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Dump truck | 65862 | SINOTRUCK | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Dump truck | 65863 | SINOTRUCK | O | 10 | 10 | 0 | 10 | 10 | 0 | 10 | 50
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WATER AND FUEL Truck | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Shower Truck | 3-ET-00821 | FIAT 682N3 | O | 8 | 8 | 0 | 8 | 8 | 0 | 8 | 40
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | FUEL TRUCK | 3-ET-69015 | IVECO | O | 6 | 6 | 0 | 8 | 8 | 0 | 6 | 34
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | FUEL TRUCK | 3-ET-69015 | IVECO | O | 6 | 6 | 0 | 6 | 6 | 0 | 6 | 30
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | WATER TRUCK RENTAL | 13187 | FIAT | O | 8 | 8 | 0 | 10 | 10 | 0 | 8 | 44
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | WATER TRUCK RENTAL | 11302 | FIAT | O | 8 | 8 | 0 | 10 | 10 | 0 | 8 | 44
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | WATER TRUCK RENTAL | 12223 | FIAT | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Cargo Truck Rental | 2351 | ISUZU | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cargo Truck Rental | G-130 | Shampo | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cargo Truck Rental |  | Shampo |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Cargo Truck Rental | 4040 | ISUZU | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | LOWBED | 63495 | Genlyon 380 | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | #REF! | #REF! | #REF! | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Cargo Truck | COOD-23/G-167 | UD | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cargo Truck | G-193 |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Cargo Truck | G-112 | UD | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Cargo Truck | G-148 | NISSAN | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LIGHT VEHICLE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Small Vehicle | 10250 | Pickup | O | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 70
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Small Vehicle | 51323 | Pickup | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Small Vehicle |  | Pickup | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Small Vehicle | 42921 | Pickup | O | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Small Vehicle | 46766 | Pickup | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Small Vehicle | 3-54411 | 5L | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Small Vehicle | 46767 | Pickup | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Small Vehicle | 46799 | Land cruizer | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Small Vehicle reantal | G-070 |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Small Vehicle rental | 71685 | Hilux Pkup | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Small Vehicle rental | 10760 | 2H | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Small Vehicle rental | 45132 | Pickup | O | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 70
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Small Vehicle rental | 62086 | Pickup | O | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 70
3.6713 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7121 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Small Vehicle rental | 49148 | Pickup | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7937 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.8345 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.8753 | Small Vehicle rental | code-50 | 2H | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9161 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9569 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9977 | Small Vehicle rental |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.0385 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.0793 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.12 | Small Vehicle rental |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1608 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2016 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Small Vehicle rental |  | Long base | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2832 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.324 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Small Vehicle rental | 30981 | Pickup | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4056 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4464 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Small Vehicle rental | 99633 | Pickup | O | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 70
4.528 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.5688 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Small Vehicle rental | 65025 | Long base | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.6503 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.6911 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Small Vehicle rental | 60681 | Long base | O |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.7727 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.8135 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Small Vehicle rental | 67618 | Long base | O |  |  |  |  | 0 | 0 | 0 | 0
4.8951 |  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.9359 |  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Small Vehicle reantal | 62485 | Long base | O | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 70
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Small Vehicle reantal | 48049 | Long base | O | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 70
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Small Vehicle reantal | 49739 | Long base | O | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 30
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Small Vehicle reantal | 8822(254) |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Small Vehicle reantal | G-066 | PRADO | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Small Vehicle reantal | G-088 | Pickup | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Small Vehicle reantal | G-024 |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Small Vehicle reantal |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Small Vehicle Rental | code-60 | dyna | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GENERATOR AND AIR COMPRESSSOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1 | #REF! | #REF! | #REF! | O | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | #REF! | 0 | 0 | 0 | 0 | 0 | 0
1 | Cunmins Power Generator | C11213 | X2562 | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | #REF! |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Generator Kama |  | KDE12EW | O | 14 | 11 | 11 | 14 | 14 | 14 | 14 | 92
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Generator Kama (Cons.) | G149100438 | Kama | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | #REF! | #REF! | RDM3000K | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | #REF! | #REF! | #REF! | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Generatoer engine |  | 198 | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HAND COMPACTORS | [10 empty] | 0
1 | HAND COMPACTOR |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | HAND COMPACTOR |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | HAND COMPACTOR |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | HAND COMPACTOR |  |  | O | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HAND COMPACTOR |  |  | O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OTHER SITE EQUIPIMENTS
| Equipiment |  | Serial No. |  | Model
| Electronic Totalstation |  | 596355 |  | NTS3624
| Electronic Totalstation |  | 594271 |  | NTS3624
| Level |  | 5149545
| Level |  | 5149247
| Level |  | B40D10385

## plan & Unit price & Direct cost (hidden)
Cross-land Construction Campany
Project: Haro sebu-Lelo-Qaqe | [10 empty] | #NAME?
Weekly Adjusted Plan | [10 empty] | #NAME?
Week 32 ((23-29)-08-07)
ITEM | DESCRIPTION | Unit | Unit Price | Direct Cost | Adjusted Plan |  | Executed |  | Direct Cost
NO. |  |  |  |  | Qty. | Amount | Qty. | Amount | Plan | Executed
GR.2. EARTH WORK
1200 | General | ls | 23000 | 0 | 1 | 2750 | 0 | 0 | 0 | 0
21.01 | Clearing & Grubbing | ha | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42.01a(ii)A | Embankment/borrow Placing | m3 | 34.71 | 22.1368 | 1218.8 | 42304.548 | 1108 | 38458.68 | 26980.2943 | 24527.5403
42.03(a) | Extra over itemm 42.01 for common(Normal)excavation to spoil | m3 | 0 | 18.927 | 0 | 0 | 0 | 0 | 0 | 0
42.01a(ii)A | Fine Grading by embankment/borrow | m3 | 13.35 | 7.8488 | 0 | 0 | 0 | 0 | 0 | 0
54.01(b) | Capping Placing(G20) | m3 | 46.8 | 19.0724 | 326.7 | 15289.56 | 297 | 13899.6 | 6230.9438 | 5664.4944
54.01(b) | Fine Grading-Capping(G20) | m3 | 5.85 | 2.9397 | 0 | 0 | 0 | 0 | 0 | 0
42.03(b) | Rock excavation to spoil | m3 | 119 | 25.573 | 460 | 54740 | 400 | 47600 | 11763.5636 | 10229.1858
Sub Total | [5 empty] | 115084.108 | 0 | 99958.28 | 44974.8017 | 40421.2204
GR.3.PAVEMENT Work | [5 empty] | 0 | 0 | 0 |  | 0
54.01(a) | Subbase Placing | m3 | 84 | 38.5373 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | [5 empty] | 0 | 0 | 0 | 0 | 0
GR.4.MINOR DRAINAGE | [8 empty] | 0
32.01(a) | Excavation of open drains | m3 | 75 | 14.7111 | 0 | 0 | 0 | 0 | 0 | 0
32.01(b) | Excavation of hard material | m3 | 115 | 14.7111 | 0 | 0 | 0 | 0 | 0 | 0
32.02(a) | Backfilling from excavated material | m3 | 100 | 24.3397 | 0 | 0 | 0 | 0 | 0 | 0
32.02(b) | Backfilling(Selected)Minor | m3 | 47.5 | 24.3397 | 0 | 0 | 0 | 0 | 0 | 0
32.03(a) | R.C. pipe(dia.36") | lm | 135 | 31.4083 | 42.35 | 5717.25 | 38.5 | 5197.5 | 1330.14 | 1209.2182
32.03(b) | R.C. pipe(dia.48") | lm | 240 | 39.2603 | 0 | 0 | 0 | 0 | 0 | 0
32.07(b)(i) | Class A Concrete ( Minor ) | m3 | 2524.2843 | 978.2776 | 0 | 0 | 0 | 0 | 0 | 0
32.10(b) | Rebar bending & Placing | Kg | 49 | 14.3785 | 0 | 0 | 0 | 0 | 0 | 0
34.03(b) | Masonory construction | m3 | 967.6584 | 263.5265 | 0 | 0 | 0 | 0 | 0 | 0
34.01(b)i | Paved construction | m2 | 89.8603 | 96.9312 | 74.1 | 6658.6467 | 45.51 | 4089.5413 | 7182.6006 | 4411.3381
Sub Total | [5 empty] | 12375.8967 |  | 9287.0413 | 8512.7406 | 5620.5563
GR.5.MAJOR DRAINAGE | [8 empty] | 0
81.02(a)iii | Excavation of soft material irrespective of depth | m3 | 135 | 14.7111 | 0 | 0 | 0 | 0 | 0 | 0
81.05(a) | Backfilling from excavated material | m3 | 120 | 24.3397 | 0 | 0 | 0 | 0 | 0 | 0
87.16(b) | Handlaid filling | m3 | 114 | 24.3397 | 0 | 0 | 0 | 0 | 0 | 0
87.16(a) | Granular material filling | m3 | 106.4 | 56.1881 | 0 | 0 | 0 | 0 | 0 | 0
84.01(a) | Concrete Class ''A'' | m3 | 3832.4205 | 1206.7676 | 0 | 0 | 144 | 551868.5499 | 0 | 173774.5352
83.01(a) & 83.01(b) | Rebar bending & Placing | Kg | 49 | 14.3785 | 0 | 0 | 0 | 0 | 0 | 0
87.07 | Concrete bridge railing with R.C posts | LM | 500 | 451.3046 | 0 | 0 | 0 | 0 | 0 | 0
89.01(a) | Masonory construction | m3 | 1064.8335 | 471.1963 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sub Total | [5 empty] | #REF! |  | #REF! | #REF! | #REF!
GR.6.Retaing wall and Mis.
92.01 | Reflective road sign | M2 | 2000 | 919.0754 | 0 | 0 | #REF! | #REF! | 0 | #REF!
92.01 | Project sign with post | pcs | 1000 | 4609.4154 | 0 | 0 | 0 | 0 | 0 | 0
92.01 | Concrete sign post | pcs | 500 | 268.4625 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | [5 empty] | 0 |  | #REF! | 0 | #REF!
Cummulative | [5 empty] | #REF! |  | #REF! | #REF! | #REF!
MATERIAL PRODUCTION | [8 empty] | 0
1 | Excavation to stock/production | m3 | 22.25 | 14.2285 | 0 | 0 | 0 | 0 | 0 | 0
3 | Capping Production(G20) | m3 | 29.25 | 11.8518 | 1056 | 30888 | #REF! | #REF! | 12515.4999 | #REF!
5 | Subbase production (Natural) | m3 | 42 | 18.9629 | 0 | 0 | #REF! | #REF! | 0 | #REF!
6 | Backfill Material Production(minor) | m3 | 31.25 | 16.1194 | 0 | 0 | 0 | 0 | 0 | 0
7 | R.C. pipe(dia.36") | Pcs | 4005 | 807.4923 | 0 | 0 | 0 | 0 | 0 | 0
8 | R.C. pipe(dia.48") | Pcs | 5280 | 809.1743 | 0 | 0 | 0 | 0 | 0 | 0
Class "A" Concrete
9 | Sand production | m3 | 16.7813 | 6.5035 | 0 | 0 | 0 | 0 | 0 | 0
10 | Stone Production ( For Aggregate by Quarryman ) | m3 | 75.053 | 29.0865 | 0 | 0 | 0 | 0 | 0 | 0
11 | Stone Production | m3 | 47.6078 | 18.4502 | 0 | 0 | 0 | 0 | 0 | 0
12 | C.agg. production | M3 | 229.792 | 89.0551 | 31.12 | 7151.1276 | 0 | 0 | 2771.3946 | 0
Class "B" Masonry
13 | Stone Production by Excavator ( For Masonary ) | m3 | 59.8224 | 16.2917 | 0 | 0 | 0 | 0 | 0 | 0
14 | Stone prodn. (Q.man) | m3 | 120.3979 | 32.7885 | 26.36 | 3173.6874 | 0 | 0 | 864.3038 | 0
15 | Sand production | m3 | 23.8806 | 6.5035 | 0 | 0 | 22.97 | 548.5384 | 0 | 149.3858
| G.R. paved water way(Paved Ditch) |  |  |  | 0 | 0 |  | 0 | 0 | 0
16 | Stone Production by Excavator ( For Masonary ) | m3 | 15.1032 | 16.2917 | 0 | 0 | 0 | 0 | 0 | 0
17 | Stone prodn. (Q.man) | m3 | 30.3966 | 32.7885 | 20.988 | 637.9643 | 0 | 0 | 688.1642 | 0
18 | Sand production | m3 | 6.0291 | 6.5035 | 0 | 0 | 19.08 | 115.0352 | 0 | 124.0871
Production of major backfill
19 | Granular material production (Natural) | m3 | 22.3 | 24.64 | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total |  |  |  |  | 41850.7792 |  | #REF! | 16839.3626 | #REF!
Material Hauling
1 | Embankment/borrow Hauling | m3 | 18.69 | 12.0901 | 1090.2 | 20375.838 | 948 | 17718.12 | 13180.6092 | 11461.3993
2 | Capping Hauling-Capping(G20) | m3 | 35.1 | 14.3865 | 528 | 18532.8 | 480 | 16848 | 7596.0845 | 6905.5314
3 | Subbase Hauling | m3 | 49 | 22.8287 | 0 | 0 | 0 | 0 | 0 | 0
4 | Backfill material Hauling(Minor) | m3 | 46.25 | 23.5866 | 0 | 0 | 0 | 0 | 0 | 0
5 | R.C. pipe(dia.36") | Lm | 360 | 71.7634 | 0 | 0 | 0 | 0 | 0 | 0
6 | R.C. pipe(dia.48") | Lm | 480 | 72.646 | 0 | 0 | 0 | 0 | 0 | 0
Class "A" Concrete
7 | Sand hauling | m3 | 74.0341 | 28.6917 | 0 | 0 | 0 | 0 | 0 | 0
8 | Stone hauling to crusher | m3 | 86.5541 | 33.5438 | 0 | 0 | 0 | 0 | 0 | 0
9 | C. agg. Hualing | m3 | 316.3329 | 122.5937 | 0 | 0 | 0 | 0 | 0 | 0
| Class "B" Masonry |  |  |  |  | 0 |  | 0 | 0 | 0
10 | Stone hauling | m3 | 522.8862 | 142.3998 | 0 | 0 | 0 | 0 | 0 | 0
11 | Sand hauling | m3 | 105.3546 | 28.6917 | 0 | 0 | 0 | 0 | 0 | 0
| G.R. paved water way(Paved Ditch) | [5 empty] | 0
12 | Stone hauling | m3 | 132.0121 | 142.3998 | 96 | 12673.1605 | 96 | 12673.1605 | 13670.3828 | 13670.3828
13 | Sand hauling | m3 | 26.5987 | 28.6917 | 12 | 319.184 | 12 | 319.184 | 344.2999 | 344.2999
Hauling of major backfill
14 | Granular material Hauling | m3 | 53.2 | 27.9175 | 144 | 7660.8 | 144 | 7660.8 | 4020.1197 | 4020.1197
| Sub Total |  |  |  |  | 59561.7825 |  | 55219.2645 | 38811.4961 | 36401.7331
Form work
Form Work Minor |  | m2 | 598.0037 | 231.7542 | 0 | 0 | 0 | 0 | 0 | 0
Form Work Major |  | m2 | #REF! | #REF! | 0 | #REF! | 0 | #REF! | #REF! | #REF!
False Work Major |  | m2 | 126.1656 | 39.7275 | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
Grand Total | [5 empty] | #REF! |  | #REF! | #REF! | #REF!
UNPAID ITEMS
Pond Construction |  | m2 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Camp construction |  | % |  |  | 0 | 0 | 0 | 0 | 0 | 0
Service Road |  | km |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0

## Direct cost summary (hidden)
Cross-land Construction Company
Project: Haro sebu-Lelo-Qaqe
DIRECT COST SUMMARY
[8 empty] | Date | 19/07/2007
[8 empty] | Budget Year | 2007
Item No | Description | Unit | Productivity |  | Actual Direct Cost (Birr) |  |  |  | Unit price Share (Birr)
|  |  | Hr | Day(8Hr) | Material | Labor | Equipment | Total DC
Bill No 1 General
1200 | General | ls | 0.43 | 3.44 | 0 | 0 | 0 | 0 | 23000
Bill No 2 Site clearance
21.01 | Clearing & Grabbing | Ha | 0.1275 | 1.02 | 0 | 0 | 0 | 0 | 35000 | 35000
Bill No 4 Earthwork
42.01 | Cut/borrow to fill |  |  |  | 16.0885 | 2.6762 | 37.5396 | 56.3042 | 89 | 89 | 16.0885 | 2.6762 | 37.5396
42.01a(ii)A | Excavation to stock/production | M3 | 85 | 680 | 3.7691 | 0.37118 | 10.0882 | 14.2285 | 22.25 |  | 3.7691 | 0.37118 | 10.0882 | 0.23427 | 0.1387
42.01a(ii)A | Embankment/borrow Hauling | M3 | 100 | 800 | 3.7231 | 0.59195 | 7.775 | 12.0901 | 18.69 |  | 3.7231 | 0.59195 | 7.775 | 0.23142
42.01a(ii)A | Embankment/borrow Placing | M3 | 68 | 544 | 5.3236 | 1.4847 | 15.3284 | 22.1368 | 34.71 |  | 5.3236 | 1.4847 | 15.3284 | 0.3309
42.01a(ii)A | Fine Grading by embankment/borrow | M3 | 484.33 | 3874.64 | 3.2726 | 0.22831 | 4.3479 | 7.8488 | 13.35 |  | 3.2726 | 0.22831 | 4.3479 | 0.20341
| Subgrade Preparation | M3 | [6 empty] | 20
42.03(a) | Cut to spoil |  |  |  | 4.8048 | 0.67119 | 13.451 | 18.927
42.03(a) | Extra over itemm 42.01 for common(Normal)excavation to spoil | M3 | 102 | 816 | 4.8048 | 0.67119 | 13.451 | 18.927 | 88 | 88
42.03(a) | Cut to spoil |  |  |  | 4.8048 | 0.67119 | 13.451 | 18.927 | 35
42.03(a) | Extra over itemm 42.01 for intermediate materials excavation to spoil | M3 | 102 | 816 | 4.8048 | 0.67119 | 13.451 | 18.927 | 99 | 88
42.03(b) | Rock excavation to spoil |  |  |  | 6.2533 | 1.4625 | 17.8571 | 25.573 | 119 | 99
42.03(b) | Extra over itemm 42.01 for excavating and breaking in rock(hard material)excavation to spoil | M3 | 59.5 | 476 | 6.2533 | 1.4625 | 17.8571 | 25.573 | 119 | 119 | 1
54.01(b) | Capping to fill(G20) |  |  |  | 13.3034 | 2.7056 | 32.2413 | 48.2504 | 117 | 117 | G20 | 77
54.01(b) | Capping Production(G20) | M3 | 102 | 816 | 3.1409 | 0.30402 | 8.4069 | 11.8518 | 29.25 | 115G7 | 0.24563 | 18.9136
54.01(b) | Capping Hauling-Capping(G20) | M3 | 100 | 800 | 4.6773 | 0.69422 | 9.015 | 14.3865 | 35.1 |  | 0.29816 | 22.9586
54.01(b) | Capping Placing(G20) | M3 | 85 | 680 | 4.8384 | 1.4791 | 12.7549 | 19.0724 | 46.8 |  | 0.39528 | 30.4365
54.01(b) | Fine Grading-Capping(G20) | M3 | 484.33 | 3874.64 | 0.64677 | 0.22831 | 2.0646 | 2.9397 | 5.85 |  | 0.060925 | 4.6912
54.01(b) | Capping to fill(G7) |  |  |  | 13.3034 | 2.7056 | 32.2413 | 48.2504 | 115 | 117 | G20 | 77
54.01(b) | Capping Production(G7) | M3 | 102 | 816 | 3.1409 | 0.30402 | 8.4069 | 11.8518 | 28.75 | 115G7 | 0.24563 | 18.9136
54.01(b) | Capping Hauling-Capping(G7) | M3 | 100 | 800 | 4.6773 | 0.69422 | 9.015 | 14.3865 | 34.5 |  | 0.29816 | 22.9586
54.01(b) | Capping Placing(G7) | M3 | 85 | 680 | 4.8384 | 1.4791 | 12.7549 | 19.0724 | 46 |  | 0.39528 | 30.4365
54.01(b) | Fine Grading-Capping(G7) | M3 | 484.33 | 3874.64 | 0.64677 | 0.22831 | 2.0646 | 2.9397 | 5.75 |  | 0.060925 | 4.6912
Bill No 5: Pavment
54.01(a) | Natural Selected Subbase |  |  |  | 21.4826 | 4.7137 | 54.1326 | 80.329 | 175 | 175
54.01(a) | Subbase production (Natural) | M3 | 63.75 | 510 | 5.0255 | 0.48643 | 13.451 | 18.9629 | 42 |  | 0.23607
54.01(a) | Subbase Hauling | M3 | 100 | 800 | 7.774 | 1.0398 | 14.015 | 22.8287 | 49 |  | 0.28419
54.01(a) | Subbase Placing | M3 | 50 | 400 | 8.6832 | 3.1875 | 26.6667 | 38.5373 | 84 |  | 0.47974
Bill No 3: Minor Drainage
32.01 | Structural excavation(Common) |  |  |  | 3.2797 | 1.244 | 10.1875 | 14.7111 | 75 | 75
32.01(a) | Excavation of open drains | M3 | 40 | 320 | 3.2797 | 1.244 | 10.1875 | 14.7111 | 75 | 80
32.01 | Structural excavation(moderate) |  |  |  | 3.2797 | 1.244 | 10.1875 | 14.7111 | 80 | 75
32.01(a) | Excavation of open drains | M3 | 40 | 320 | 3.2797 | 1.244 | 10.1875 | 14.7111 | 80 | 80
32.01(b) | Structural excavation(Hard) |  |  |  | 3.2797 | 1.244 | 10.1875 | 14.7111 | 115 | 115
32.01(b) | Excavation of hard material | M3 | 40 | 320 | 3.2797 | 1.244 | 10.1875 | 14.7111 | 115
32.02(a) | Backfill from excavated material |  |  |  | 5.1958 | 14.6258 | 4.5181 | 24.3397 | 100 | 100
32.02(a) | Backfilling from excavated material | M3 | 3.32 | 26.56 | 5.1958 | 14.6258 | 4.5181 | 24.3397 | 100
32.02(b) | Backfill from selected material |  |  |  | 17.4062 | 16.5261 | 30.1134 | 64.0457 | 125 | 125
32.02(b) | Backfill Material Production(minor) | M3 | 35 | 280 | 3.728 | 0.74863 | 11.6429 | 16.1194 | 31.25 |  | 0.25169
32.02(b) | Backfill material Hauling(Minor) | M3 | 100 | 800 | 8.4825 | 1.1516 | 13.9525 | 23.5866 | 46.25 |  | 0.36828
32.02(b) | Backfilling(Selected)Minor | M3 | 3.32 | 26.56 | 5.1958 | 14.6258 | 4.5181 | 24.3397 | 47.5 |  | 0.38004
87.16(b) | Handlaid rock fill For retaining Wall |  |  |  | 17.4062 | 16.5261 | 30.1134 | 64.0457 | 200 | 300
87.16(b) | Handlaid Material Production | M3 | 35 | 280 | 3.728 | 0.74863 | 11.6429 | 16.1194 | 50 |  | 0.25169
87.16(b) | Handlaid material Hauling | M3 | 100 | 800 | 8.4825 | 1.1516 | 13.9525 | 23.5866 | 74 |  | 0.36828
87.16(b) | Handlaid filling | M3 | 3.32 | 26.56 | 5.1958 | 14.6258 | 4.5181 | 24.3397 | 76 |  | 0.38004
32.03(a) | R.C. pipe(dia.36") |  |  |  | 825.3602 | 38.8238 | 46.48 | 910.664 | 4500 | 4500
32.03(a) | R.C. Pipe Production(dia.36") | Pcs | 1.25 | 10 | 771.7047 | 19.3077 | 16.48 | 807.4923 | 4005 |  | 0.88671
32.03(a) | Pipe hauling(dia.36") | Pcs | 2 | 16 | 34.5 | 7.2634 | 30 | 71.7634 | 360 |  | 0.078803
32.03(a) | Installation and curing(dia.36") | Pcs | 3.75 | 30 | 19.1555 | 12.2527 | 0 | 31.4083 | 135 |  | 0.034489
32.03(a) | R.C. pipe(dia.42") |  |  |  | 825.3602 | 38.8238 | 46.48 | 910.664 | 5400 | 4500
32.03(a) | R.C. Pipe Production(dia.42") | Pcs | 1.25 | 10 | 771.7047 | 19.3077 | 16.48 | 807.4923 | 4806 |  | 0.88671
32.03(a) | Pipe hauling(dia.42") | Pcs | 2 | 16 | 34.5 | 7.2634 | 30 | 71.7634 | 432 |  | 0.078803
32.03(a) | Installation and curing(dia.42") | Pcs | 3.75 | 30 | 19.1555 | 12.2527 | 0 | 31.4083 | 162 |  | 0.034489
32.03(b) | R.C. pipe(dia.48") |  |  | 0 | 830.3398 | 43.5741 | 47.1667 | 921.0806 | 6000 | 5400
32.03(b) | R.C. Pipe Production(dia.48") | Pcs | 1.2 | 9.6 | 771.8954 | 20.1122 | 17.1667 | 809.1743 | 5280 | 6000 | 0.87851
32.03(b) | Pipe hauling(dia.48") | Pcs | 1.5 | 12 | 34.5 | 8.146 | 30 | 72.646 | 480 |  | 0.07887
32.03(b) | Installation and curing(dia.48") | Pcs | 3 | 24 | 23.9444 | 15.3159 | 0 | 39.2603 | 240 |  | 0.042624
32.07(b)(i) | Class 'A' Concrete(Minor) |  |  |  | 1363.8349 | 205.0161 | 232.9889 | 1898.978 | 4900 | 4900
32.07(b)(i) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 16.7813 |  | 0.0034247
32.07(b)(i) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 74.0341 |  | 0.015109
32.07(b)(i) | Stone Production ( For Aggregate by Quarryman ) | M3 | 2 | 16 | 0 | 29.0865 | 0 | 29.0865 | 75.053 |  | 0.015317
32.07(b)(i) | Stone Production | M3 | 30 | 240 | 4.2435 | 0.8734 | 13.3333 | 18.4502 | 47.6078 |  | 0.0097159
32.07(b)(i) | Stone hauling to crusher | M3 | 5 | 40 | 9.9187 | 6.375 | 17.25 | 33.5438 | 86.5541 |  | 0.017664
32.07(b)(i) | C.agg. production | M3 | 2.5 | 20 | 20.257 | 18.7981 | 50 | 89.0551 | 229.792 |  | 0.046896
32.07(b)(i) | C. agg. Hualing | M3 | 100 | 800 | 42.5453 | 5.7334 | 74.315 | 122.5937 | 316.3329 |  | 0.064558
32.07(b)(i) | Form work | M2 | 2 | 16 | 187.4004 | 43.4163 | 0.9375 | 231.7542 | 598.0037 |  | 0.12204
32.07(b)(i) | Falsework | M3 | 3.5 | 28 | 13.363 | 22.0306 | 0 | 361.0216 | 931.5569 |  | 0.19011
32.07(b)(i) | Class A Concrete ( Minor ) | M3 | 3.2812 | 26.25 | 1074.8749 | 77.0356 | 54.8571 | 978.2776 | 2524.2843 |  | 0.51516
32.07(b)(i) | Class 'C' Concrete(Minor) |  |  |  | 1363.8349 | 205.0161 | 232.9889 | 1898.978 | 4700 | 4900
32.07(b)(i) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 16.0963 |  | 0.0034247
32.07(b)(i) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 71.0123 |  | 0.015109
32.07(b)(i) | Stone Production ( For Aggregate by Quarryman ) | M3 | 2 | 16 | 0 | 29.0865 | 0 | 29.0865 | 71.9896 |  | 0.015317
32.07(b)(i) | Stone Production | M3 | 30 | 240 | 4.2435 | 0.8734 | 13.3333 | 18.4502 | 45.6646 |  | 0.0097159
32.07(b)(i) | Stone hauling to crusher | M3 | 5 | 40 | 9.9187 | 6.375 | 17.25 | 33.5438 | 83.0213 |  | 0.017664
32.07(b)(i) | C.agg. production | M3 | 2.5 | 20 | 20.257 | 18.7981 | 50 | 89.0551 | 220.4128 |  | 0.046896
32.07(b)(i) | C. agg. Hualing | M3 | 100 | 800 | 42.5453 | 5.7334 | 74.315 | 122.5937 | 303.4213 |  | 0.064558
32.07(b)(i) | Form work | M2 | 2 | 16 | 187.4004 | 43.4163 | 0.9375 | 231.7542 | 573.5953 |  | 0.12204
32.07(b)(i) | Falsework | M3 | 3.5 | 28 | 13.363 | 22.0306 | 0 | 361.0216 | 893.5341 |  | 0.19011
32.07(b)(i) | Class A Concrete ( Minor ) | M3 | 3.2812 | 26.25 | 1074.8749 | 77.0356 | 54.8571 | 978.2776 | 2421.2523 |  | 0.51516
32.10(b) | Reinforcment bar |  |  |  | 13.3356 | 0.66474 | 0.37812 | 14.3785 | 49 | 49
32.10(b) | Rebar bending & Placing | Kg | 80 | 640 | 13.3356 | 0.66474 | 0.37812 | 14.3785 | 49
34.03(b) | Class 'B' masonry |  |  |  | 498.5959 | 120.8708 | 177.0459 | 490.2017 | 1800 | 1800
34.03(b) | Stone Production by Excavator ( For Masonary ) | M3 | 30 | 240 | 10.5498 | 0.80128 | 13.3333 | 16.2917 | 59.8224 |  | 0.033235
34.03(b) | Stone prodn. (Q.man) | M3 | 0.9 | 7.2 | 0 | 49.6795 | 0 | 32.7885 | 120.3979 |  | 0.066888
34.03(b) | Stone hauling | M3 | 100 | 800 | 74.5818 | 10.1755 | 131 | 142.3998 | 522.8862 |  | 0.29049
34.03(b) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 23.8806 |  | 0.013267
34.03(b) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 105.3546 |  | 0.05853
34.03(b) | Masonory construction | M3 | 1.44 | 11.52 | 402.2323 | 58.5473 | 10.4167 | 263.5265 | 967.6584 |  | 0.53759
34.01(b)i | G.R. paved water way(Paved Ditch) | M2 |  |  | 154.6953 | 100.923 | 166.6292 | 323.6063 | 300 | 300
34.01(b)i | Stone Production by Excavator ( For Masonary ) | M3 | 30 | 240 | 10.5498 | 0.80128 | 13.3333 | 16.2917 | 15.1032 |  | 0.050344
34.01(b)i | Stone prodn. (Q.man) | M3 | 0.9 | 7.2 | 0 | 49.6795 | 0 | 32.7885 | 30.3966 |  | 0.10132
34.01(b)i | Stone hauling | M3 | 100 | 800 | 74.5818 | 10.1755 | 131 | 142.3998 | 132.0121 |  | 0.44004
34.01(b)i | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 6.0291 |  | 0.020097
34.01(b)i | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 26.5987 |  | 0.088662
34.01(b)i | Paved construction | M2 | 1 | 8 | 58.3317 | 38.5995 | 0 | 96.9312 | 89.8603 |  | 0.29953
34.01(b)i | G.R. paved water way(Pipe) | M2 |  |  | 154.6953 | 100.923 | 166.6292 | 323.6063 | 300 | 300
34.01(b)i | Stone Production by Excavator ( For Masonary ) | M3 | 30 | 240 | 10.5498 | 0.80128 | 13.3333 | 16.2917 | 15.1032 |  | 0.050344
34.01(b)i | Stone prodn. (Q.man) | M3 | 0.9 | 7.2 | 0 | 49.6795 | 0 | 32.7885 | 30.3966 |  | 0.10132
34.01(b)i | Stone hauling | M3 | 100 | 800 | 74.5818 | 10.1755 | 131 | 142.3998 | 132.0121 |  | 0.44004
34.01(b)i | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 6.0291 |  | 0.020097
34.01(b)i | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 26.5987 |  | 0.088662
34.01(b)i | Paved construction | M2 | 1 | 8 | 58.3317 | 38.5995 | 0 | 96.9312 | 89.8603 |  | 0.29953
| Bill No 5: Major Drainage | [8 empty] | 135
81.02(a)iii | Structural excavation |  |  |  | 3.2797 | 1.244 | 10.1875 | 14.7111 | 135 | 200
81.02(a)iii | Excavation of soft material irrespective of depth | M3 | 40 | 320 | 3.2797 | 1.244 | 10.1875 | 14.7111 | 135 | 500
81.02(a)iii | Structural excavation(Intermidiate) |  |  |  | 3.2797 | 1.244 | 10.1875 | 14.7111 | 200 | 200
81.02(a)iii | Excavation of intermidiate material irrespective of depth | M3 | 40 | 320 | 3.2797 | 1.244 | 10.1875 | 14.7111 | 200 | 500
81.02(a)iii | Structural excavation(Hard) |  |  |  | 3.2797 | 1.244 | 10.1875 | 14.7111 | 500 | 200
81.02(a)iii | Excavation of Hard material irrespective of depth | M3 | 40 | 320 | 3.2797 | 1.244 | 10.1875 | 14.7111 | 500 | 500
81.05(a) | Backfill from excavated material |  |  |  | 5.1958 | 14.6258 | 4.5181 | 24.3397 | 120 | 120
81.05(a) | Backfilling from excavated material | M3 | 3.32 | 26.56 | 5.1958 | 14.6258 | 4.5181 | 24.3397 | 120
87.16(b) | Handlaid rock fill |  |  |  | 17.4062 | 16.5261 | 30.1134 | 64.0457 | 300 | 300
87.16(b) | Handlaid Material Production | M3 | 35 | 280 | 3.728 | 0.74863 | 11.6429 | 16.1194 | 75 |  | 0.25169
87.16(b) | Handlaid material Hauling | M3 | 100 | 800 | 8.4825 | 1.1516 | 13.9525 | 23.5866 | 111 |  | 0.36828
87.16(b) | Handlaid filling | M3 | 3.32 | 26.56 | 5.1958 | 14.6258 | 4.5181 | 24.3397 | 114 |  | 0.38004
87.16(a) | Selected granular backfill |  |  |  | 34.143 | 19.3518 | 46.7301 | 100.225 | 190 | 190
87.16(a) | Granular material production (Natural) | M3 | 35 | 280 | 3.728 | 0.74863 | 11.6429 | 16.1194 | 30.4 |  | 0.16083
87.16(a) | Granular material Hauling | M3 | 100 | 800 | 9.632 | 1.2705 | 17.015 | 27.9175 | 53.2 |  | 0.27855
87.16(a) | Granular material filling | M3 | 3.32 | 26.56 | 20.7831 | 17.3326 | 18.0723 | 56.1881 | 106.4 |  | 0.56062
84.01(a) | Class 'A' Concrete |  |  |  | 1180.7685 | 161.5998 | 232.0514 | 1574.4196 | 5000 | 5000
84.01(a) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 20.6537 | 4900 | 0.0041307
84.01(a) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 91.1182 | 4800 | 0.018224
84.01(a) | Stone Production ( For Aggregate by Quarryman ) | M3 | 2 | 16 | 0 | 29.0865 | 0 | 29.0865 | 92.3723 | 4000 | 0.018474
84.01(a) | Stone Production | M3 | 30 | 240 | 4.2435 | 0.8734 | 13.3333 | 18.4502 | 58.5938 | 3800 | 0.011719
84.01(a) | Stone hauling to crusher | M3 | 5 | 40 | 9.9187 | 6.375 | 17.25 | 33.5438 | 106.5273 |  | 0.021305
84.01(a) | C.agg. production | M3 | 2.5 | 20 | 20.257 | 18.7981 | 50 | 89.0551 | 282.8188 |  | 0.056564
84.01(a) | C. agg. Hualing | M3 | 100 | 800 | 42.5453 | 5.7334 | 74.315 | 122.5937 | 389.3298 |  | 0.077866
84.01(a) | Falsework | M3 | 3.5 | 28 | 17.697 | 22.0306 | 0 | 39.7275 | 126.1656 |  | 0.025233
84.01(a) | Concrete Class ''A'' | M3 | 3.2812 | 26.25 | 1074.8749 | 77.0356 | 54.8571 | 1206.7676 | 3832.4205 |  | 0.76648
84.01(a) | Class 'C-25' Concrete |  |  |  | 1180.7685 | 161.5998 | 232.0514 | 1574.4196 | 4900 | 5000
84.01(a) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 20.2406 | 4900 | 0.0041307
84.01(a) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 89.2958 | 4800 | 0.018224
84.01(a) | Stone Production ( For Aggregate by Quarryman ) | M3 | 2 | 16 | 0 | 29.0865 | 0 | 29.0865 | 90.5248 | 4000 | 0.018474
84.01(a) | Stone Production | M3 | 30 | 240 | 4.2435 | 0.8734 | 13.3333 | 18.4502 | 57.4219 | 3800 | 0.011719
84.01(a) | Stone hauling to crusher | M3 | 5 | 40 | 9.9187 | 6.375 | 17.25 | 33.5438 | 104.3968 |  | 0.021305
84.01(a) | C.agg. production | M3 | 2.5 | 20 | 20.257 | 18.7981 | 50 | 89.0551 | 277.1624 |  | 0.056564
84.01(a) | C. agg. Hualing | M3 | 100 | 800 | 42.5453 | 5.7334 | 74.315 | 122.5937 | 381.5432 |  | 0.077866
84.01(a) | Falsework | M3 | 3.5 | 28 | 17.697 | 22.0306 | 0 | 39.7275 | 123.6423 |  | 0.025233
84.01(a) | Concrete C-25 | M3 | 3.2812 | 26.25 | 1074.8749 | 77.0356 | 54.8571 | 1206.7676 | 3755.7721 |  | 0.76648
84.01(a) | Class 'C-20' Concrete |  |  |  | 1180.7685 | 161.5998 | 232.0514 | 1574.4196 | 4800 | 5000
84.01(a) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 19.8275 | 4900 | 0.0041307
84.01(a) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 87.4735 | 4800 | 0.018224
84.01(a) | Stone Production ( For Aggregate by Quarryman ) | M3 | 2 | 16 | 0 | 29.0865 | 0 | 29.0865 | 88.6774 | 4000 | 0.018474
84.01(a) | Stone Production | M3 | 30 | 240 | 4.2435 | 0.8734 | 13.3333 | 18.4502 | 56.25 | 3800 | 0.011719
84.01(a) | Stone hauling to crusher | M3 | 5 | 40 | 9.9187 | 6.375 | 17.25 | 33.5438 | 102.2663 |  | 0.021305
84.01(a) | C.agg. production | M3 | 2.5 | 20 | 20.257 | 18.7981 | 50 | 89.0551 | 271.5061 |  | 0.056564
84.01(a) | C. agg. Hualing | M3 | 100 | 800 | 42.5453 | 5.7334 | 74.315 | 122.5937 | 373.7566 |  | 0.077866
84.01(a) | Falsework | M3 | 3.5 | 28 | 17.697 | 22.0306 | 0 | 39.7275 | 121.119 |  | 0.025233
84.01(a) | Concrete C-20 | M3 | 3.2812 | 26.25 | 1074.8749 | 77.0356 | 54.8571 | 1206.7676 | 3679.1237 |  | 0.76648
84.01(a) | Class 'C-15' Concrete |  |  |  | 1180.7685 | 161.5998 | 232.0514 | 1574.4196 | 4000 | 5000
84.01(a) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 16.523 | 4900 | 0.0041307
84.01(a) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 72.8946 | 4800 | 0.018224
84.01(a) | Stone Production ( For Aggregate by Quarryman ) | M3 | 2 | 16 | 0 | 29.0865 | 0 | 29.0865 | 73.8978 | 4000 | 0.018474
84.01(a) | Stone Production | M3 | 30 | 240 | 4.2435 | 0.8734 | 13.3333 | 18.4502 | 46.875 | 3800 | 0.011719
84.01(a) | Stone hauling to crusher | M3 | 5 | 40 | 9.9187 | 6.375 | 17.25 | 33.5438 | 85.2219 |  | 0.021305
84.01(a) | C.agg. production | M3 | 2.5 | 20 | 20.257 | 18.7981 | 50 | 89.0551 | 226.255 |  | 0.056564
84.01(a) | C. agg. Hualing | M3 | 100 | 800 | 42.5453 | 5.7334 | 74.315 | 122.5937 | 311.4638 |  | 0.077866
84.01(a) | Falsework | M3 | 3.5 | 28 | 17.697 | 22.0306 | 0 | 39.7275 | 100.9325 |  | 0.025233
84.01(a) | Concrete C-15 | M3 | 3.2812 | 26.25 | 1074.8749 | 77.0356 | 54.8571 | 1206.7676 | 3065.9364 |  | 0.76648
84.01(a) | Class 'C-5' Concrete |  |  |  | 1180.7685 | 161.5998 | 232.0514 | 1574.4196 | 3800 | 5000
84.01(a) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 15.6968 | 4900 | 0.0041307
84.01(a) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 69.2498 | 4800 | 0.018224
84.01(a) | Stone Production ( For Aggregate by Quarryman ) | M3 | 2 | 16 | 0 | 29.0865 | 0 | 29.0865 | 70.2029 | 4000 | 0.018474
84.01(a) | Stone Production | M3 | 30 | 240 | 4.2435 | 0.8734 | 13.3333 | 18.4502 | 44.5313 | 3800 | 0.011719
84.01(a) | Stone hauling to crusher | M3 | 5 | 40 | 9.9187 | 6.375 | 17.25 | 33.5438 | 80.9608 |  | 0.021305
84.01(a) | C.agg. production | M3 | 2.5 | 20 | 20.257 | 18.7981 | 50 | 89.0551 | 214.9423 |  | 0.056564
84.01(a) | C. agg. Hualing | M3 | 100 | 800 | 42.5453 | 5.7334 | 74.315 | 122.5937 | 295.8906 |  | 0.077866
84.01(a) | Falsework | M3 | 3.5 | 28 | 17.697 | 22.0306 | 0 | 39.7275 | 95.8859 |  | 0.025233
84.01(a) | Concrete C-5 | M3 | 3.2812 | 26.25 | 1074.8749 | 77.0356 | 54.8571 | 1206.7676 | 2912.6396 |  | 0.76648
83.01(a) & 83.01(b) | Reinforcment bar |  |  |  | 13.3356 | 0.66474 | 0.37812 | 14.3785 | 49
83.01(a) & 83.01(b) | Rebar bending & Placing | Kg | 80 | 640 | 13.3356 | 0.66474 | 0.37812 | 14.3785 | 49
83.01(a) & 83.01(b) | Form work(Major) |  |  |  | 13.3356 | 0.66474 | 0.37812 | 14.3785 | 1000
83.01(a) & 83.01(b) | Form work(Major) | Kg | 80 | 640 | 13.3356 | 0.66474 | 0.37812 | 14.3785 | 1000
87.03 | Elastomeric Bearing |  |  |  | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 30000
87.03 | Plate Bearing [0.45*0.35*0.05] | pcs | 0.9825 | 7.86 | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 30000
87.07 | Concrete bridge railing with R.C posts |  |  |  | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 500
87.07 | Concrete bridge railing with R.C posts | LM | 0.9825 | 7.86 | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 500
87.07(b) | Concrete parapets and railing |  |  |  | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 500
87.07 | Concrete parapets and railing | LM | 0.9825 | 7.86 | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 500
87.19(a) | Drainage pipes and weep holes |  |  |  | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 200
87.19 | Drainage pipes and weep holes | No | 0.9825 | 7.86 | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 200
87.13 | Expansion joint |  |  |  | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 100
(a) | Expansion joint including 20mm commpressible joint filler board | LM | 0.9825 | 7.86 | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 100
87.16 | Sealing joints with |  |  |  | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 100
(a) | joint sealant, 20mm deep grouted poly sulphide sealant | LM | 0.9825 | 7.86 | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 100
89.01(a) | Class 'B' masonry |  |  |  | 498.5959 | 120.8708 | 177.0459 | 796.5126 | 1800 | 1800
89.01(a) | Stone Production by Excavator ( For Masonary ) | M3 | 30 | 240 | 10.5498 | 0.80128 | 13.3333 | 24.6844 | 55.783 |  | 0.030991
89.01(a) | Stone prodn. (Q.man) | M3 | 0.9 | 7.2 | 0 | 49.6795 | 0 | 49.6795 | 112.2682 |  | 0.062371
89.01(a) | Stone hauling | M3 | 100 | 800 | 74.5818 | 10.1755 | 131 | 215.7573 | 487.5794 |  | 0.27088
89.01(a) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 14.697 |  | 0.008165
89.01(a) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 64.8389 |  | 0.036022
89.01(a) | Masonory construction | M3 | 1.44 | 11.52 | 402.2323 | 58.5473 | 10.4167 | 471.1963 | 1064.8335 |  | 0.59157
89.01(b) | Pointing of both abutment and WWs with 1:4 mortar |  |  |  | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 100
89.01(b) | Pointing of both abutment and WWs with 1:4 mortar | M2 | 0.9825 | 7.86 | 359.6002 | 68.8037 | 22.9008 | 451.3046 | 100
89.01(a) | Class 'B' masonry(cut off wall) |  |  |  | 498.5959 | 120.8708 | 177.0459 | 796.5126 | 1800 | 1800
89.01(a) | Stone Production by Excavator ( For Masonary ) | M3 | 30 | 240 | 10.5498 | 0.80128 | 13.3333 | 24.6844 | 55.783 |  | 0.030991
89.01(a) | Stone prodn. (Q.man) | M3 | 0.9 | 7.2 | 0 | 49.6795 | 0 | 49.6795 | 112.2682 |  | 0.062371
89.01(a) | Stone hauling | M3 | 100 | 800 | 74.5818 | 10.1755 | 131 | 215.7573 | 487.5794 |  | 0.27088
89.01(a) | Sand production | M3 | 85 | 680 | 1.4894 | 0.30826 | 4.7059 | 6.5035 | 14.697 |  | 0.008165
89.01(a) | Sand hauling | M3 | 100 | 800 | 9.7427 | 1.359 | 17.59 | 28.6917 | 64.8389 |  | 0.036022
89.01(a) | Masonory construction | M3 | 1.44 | 11.52 | 402.2323 | 58.5473 | 10.4167 | 471.1963 | 1064.8335 |  | 0.59157
| Group IV: Miscelaniouse | [6 empty] | 0
92.01 | Reflective road sign |  |  |  | 906.21 | 0.86538 | 12 | 919.0754 | 2000
92.01 | Reflective road sign | M2 | 5 | 40 | 906.21 | 0.86538 | 12 | 919.0754 | 2000
94.01 | Project sign with post |  |  |  | 4531.05 | 34.6154 | 43.75 | 4609.4154 | 1000
92.01 | Project sign with post | pcs | 0.25 | 2 | 4531.05 | 34.6154 | 43.75 | 4609.4154 | 1000
92.01 | Concrete sign post |  |  |  | 228.6042 | 9.8583 | 30 | 268.4625 | 500
92.01 | Concrete sign post | pcs | 2 | 16 | 228.6042 | 9.8583 | 30 | 268.4625 | 500

## Weekly Machinery Ex
Cross-land Construction Campany
Project: Haro sebu-Lelo-Qaqe
| Weekly Machinery and Fuel Status | [13 empty] | Week 32 ((23-29)-08-07)
0
No | Type | Plat No. | Model | Planned Hrs | Oprational | Idle | Down | Rate p/h | Cost |  |  |  | Efficiency % 1/(0) | Utilizn % 1/(1+2) | Avail. % (1+2)/(0) | Standard Fuel Consumption Per Hour | Expected Fuel Consumption | Fuel
[9 empty] | Planned | Operation | Idle | Down | [7 empty] | 365977.7
Dozer
1 | Dozer | 9EM 08520 | CAT D8R | 136 | 84.25 | 30.91 | 0.33 | 1190 | 161840 | 100257.5 | 5517.435 | 392.7 | 61.95% | 73.16% | 84.68% | 42 | 3538.5 | 4526 | 5712
2 | Dozer | D8R 08518 | CAT D8R | 86 | 59.24 | 13.92 | 0 | 1190 | 102340 | 70495.6 | 2484.72 | 0 | 68.88% | 80.97% | 85.07% | 42 | 2488.08 | 2045 | 3612
3 | Dozer | D8R 03152 | CAT D8R | 136 | 86.99 | 29.83 | 0 | 1190 | 161840 | 103518.1 | 5324.655 | 0 | 63.96% | 74.46% | 85.9% | 42 | 3653.58 | 4530
| Sub Total |  |  | 358 | 230.48 | 74.66 | 0.33 |  | 426020 | 274271.2 | 13326.81 | 392.7 | 1.948 | 2.286 | 2.5564 |  | 9680.16 | 11101 | 9324
Grader | [18 empty] | 0
1 | Grader | 0498 | XG 31802 | 68 | 47.83 | 11.2 | 0 | 850 | 57800 | 40655.5 | 1428 | 0 | 70.34% | 81.03% | 86.81% | 18 | 860.94 | 624 | 1224
2 | Grader | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% | 18 | 0 | #REF! | 0
| Sub Total |  |  |  | 47.83 | 11.2 | 0 |  | 57800 | 40655.5 | 1428 | 0 |  |  |  |  | 860.94 | 624 | 1224
Roller | [18 empty] | 0
1 | Roller | 0166 | XGMA | 56 | 12.5 | 35.5 | 0 | 340 | 19040 | 4250 | 1810.5 | 0 | 22.32% | 26.04% | 85.71% | 10 | 125 | 161 | 560
2 | Roller | 0167 | XGMA | 56 | 21.83 | 25.5 | 0 | 340 | 19040 | 7422.2 | 1300.5 | 0 | 38.98% | 46.12% | 84.52% | 10 | 218.3 | 124 | 560
| Sub Total |  |  |  | 34.33 | 61 | 0 |  | 38080 | 11672.2 | 3111 | 0 | 0.61304 | 0.72165 | 1.7023 |  | 343.3 | 285 | 1120
Loader | [18 empty] | 0
1 | Loader | 0152 | XG953H | 68 | 48.87 | 14.83 | 0 | 340 | 23120 | 16615.8 | 756.33 | 0 | 71.87% | 76.72% | 93.68% | 12 | 586.44 | 559 | 816
2 | Loader | 0300 | XG953H | 68 | 25.75 | 34.25 | 0 | 340 | 23120 | 8755 | 1746.75 | 0 | 37.87% | 42.92% | 88.24% | 12 | 309 | 381 | 816
3 | Loader | 148 | XG953H | 68 | 41.2 | 24 | 0 | 340 | 23120 | 14008 | 1224 | 0 | 60.59% | 63.19% | 95.88% | 12 | 494.4 | 510
4 | Loader | 781 | XG953H | 30 | 0 | 0 | 0 | 340 | 10200 | 0 | 0 | 0 | 0% | 0% | 0% | 12 | 0 | #REF!
| Sub Total |  |  | 204 | 115.82 | 73.08 | 0 |  | 69360 | 39378.8 | 3727.08 | 0 | 1.7032 | 1.8283 | 2.7779 |  | 1389.84 | 1450 | 1632
Excavator | [18 empty] | 0
1 | Excavator | 5657 | DX-340 | 80 | 38.5 | 15.8 | 0 | 680 | 54400 | 26180 | 1611.6 | 0 | 48.12% | 70.9% | 100% | 20 | 770 | 586 | 1600
2 | Excavator | N6LA4888 | E385 |  | 0 | 0 | 0 | 840 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% | 20 | 0 | #REF! | 0
| Sub Total |  |  | 80 | 38.5 | 15.8 | 0 | 680 | 54400 | 26180 | 1611.6 | 0 |  |  | 1 |  | 770 | 586 | 0
Crusher | [18 empty] | 0
1 | crusher | XXX-06-20500153 | 495AG | 60 | 32.5 | 24.5 | 0 | 476 | 28560 | 15470 | 1749.3 | 0 | 54.17% | 57.02% | 95% | 2 | 65 | 21 | 120
| Sub Total |  |  | 60 | 32.5 | 24.5 | 0 |  | 28560 | 15470 | 1749.3 | 0 | 0.54167 | 0.57018 | 0.95 |  | 65 | 21 | 120
Mixer | [18 empty] | 0
1 | MIXER LOMBARDINI | 1DK/M486 | 15D3505.360 | 3 | 0 | 0 | 0 | 21.25 | 63.75 | 0 | 0 | 0 | 0% | 0% | 0% | 1 | 0 | 0 | 3
2 | MIXER LOMBARDINI | - | 5750 HOPPER |  | 0 | 0 | 0 | 21.25 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% |  | 0 | #REF! | 0
3 | Mixer | 0 | 0 |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% |  |  |  | 0
4 | Mixer | 0 | 5750 HOPPER |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
4 | Mixer |  |  |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0 | 0 | 0 | 0
| Sub Total |  |  |  | 0 | 0 | 0 |  | 63.75 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Vibrater | [18 empty] | 0
1 | Vibrator Petrol |  |  | 60 | 0 | 0 | 0 | 5 | 300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
2 | Vibrator Petrol |  |  | 60 | 0 | 0 | 0 | 5 | 300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
3 | Vibrator Petrol |  |  | 60 | 0 | 0 | 0 | 5 | 300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
4 | Vibrator Petrol |  |  | 60 | 0 | 0 | 0 | 5 | 300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
5 | Vibrator Petrol |  |  | 60 | 0 | 0 | 0 | 5 | 300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
6 | Vibrator Petrol |  |  | 60 | 0 | 0 | 0 | 5 | 300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
| Sub Total |  |  | 360 | 0 | 0 | 0 |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total |  |  | 360 | 0 | 0 | 0 |  | 1800 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
Water Pump | [18 empty] | 0
1 | Water Pump |  |  | 10 | 0 | 0 | 0 | 5 | 50 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0 | 0
2 | Water Pump |  |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% |  |  |  | 0
3 | Water Pump |  |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% |  |  |  | 0
4 | Water Pump |  |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% |  |  |  | 0
5 | Water Pump |  |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% |  |  |  | 0
6 | Water Pump |  |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% |  |  |  | 0
| Sub Total |  |  | 10 | 0 | 0 | 0 |  | 50 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
| Air Compressor | [17 empty] | 0
1 | Air Compressor |  |  | 60 | 0 | 0 | 0 | 5 | 300 | 0 | 0 | 0 | [6 empty] | 0
| Sub Total |  |  |  | 0 | 0 | 0 |  | 300 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
Dump Truck(Own) | [18 empty] | 0
1 | Dump truck (Genlyon) | 3-ET-61220 | Genlyon 380 | 68 | 54 | 0 | 0 | 212.5 | 14450 | 11475 | 0 | 0 | 79.41% | 100% | 79.41% | 10 | 540 | 432 | 680
2 | Small Dump Truck (Nissan) | 3-ET-10467 | Nissan | 56 | 0 | 0 | 48 | 68 | 3808 | 0 | 0 | 3264 | 0% | 0% | 0% | 10 | 0 | 0 | 560
3 | Dump truck | 3-ET-70117 | SINOTRUCK | 68 | 48 | 10 | 0 | 212.5 | 14450 | 10200 | 318.75 | 0 | 70.59% | 82.76% | 100% | 10 | 480 | 213 | 680
4 | Dump truck | 3-ET-57870 | SINOTRUCK | 20 | 0 | 0 | 0 | 212.5 | 4250 | 0 | 0 | 0 | 0% | 0% | 0% | 10 | 0
| Sub Total |  |  | 192 | 102 | 10 | 48 |  | 32708 | 21675 | 318.75 | 3264 |  |  |  |  | 1020 | 645 | 1920
1 | Shower Truck | 3-ET-00821 | FIAT 682N3 | 56 | 40 | 8 | 0 | 68 | 3808 | 2720 | 81.6 | 0 | 71.43% | 83.33% | 85.71% | 8 | 320 | 175 | 448
2 | Fuel Truck | 3-ET-69015 | IVECO | 56 | 34 | 8 | 0 | 68 | 3808 | 2312 | 81.6 | 0 | 60.71% | 80.95% | 75% | 8 | 272 | 91 | 448
3 | Fuel Truck | 3-ET-26317 | IVECO | 56 | 30 | 3 | 0 | 68 | 3808 | 2040 | 30.6 | 0 | 53.57% | 90.91% | 58.93% | 8 | 240 | 130 | 448
| Sub Total |  |  | 168 | 104 | 19 | 0 |  | 11424 | 7072 | 193.8 | 0 | 1.8571 | 2.5519 | 2.1964 |  | 832 | 396 | 1344
1 | Lowbed | 63495 | Genlyon 380 |  | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 |  | 0 |  | 15 | 0 | 0 | 0
| Sub Total |  |  | 0 | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Light Vehicle own | [18 empty] | 0
1 | Small Vehicle | 10250 | Pickup | 70 | 70 | 0 | 0 | 119 | 8330 | 8330 | 0 | 0 | 100% | 100% | 100% | 4 | 280 | 0 | 280
2 | Small Vehicle | 51323 | Pickup |  | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 0
3 | Small Vehicle | 51307 | Pickup |  | 0 | 0 | 0 | 113.75 | 0 | 0 | 0 | 0 |  | 0% | 0% | 4 | 0 | 0 | 0
4 | Small Vehicle | 46767 | Pickup |  | 0 | 0 | 0 | 113.75 | 0 | 0 | 0 | 0 |  | 0% | 0% | 4 | 0 | #REF! | 0
5 | Small Vehicle | 46799 | Land cruizer |  | 0 | 0 | 0 | 113.75 | 0 | 0 | 0 | 0 |  | 0% | 0% | 4 | 0 | #REF! | 0
| Sub Total |  |  |  | 70 | 0 | 0 |  | 8330 | 8330 | 0 | 0 | 1 | 1 | 1 |  | 280 | 0 | 280
Generatoer | [18 empty] | 0
1 | Generatoer engine | 896732 | RDM3000K | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0
1 | Generatoer engine | 253756 | RDM3000K | 60 | 0 | 0 | 0 | 50 | 3000 | 0 | 0 | 0 | #DIV/0! | 0% | 0% | 0 | 0 | 0 | 0
1 | Cunmins Power Generator | C11213 | X2562 | 122.5 | 0 | 0 | 0 | 42.5 | 5206.25 | 0 | 0 | 0 | 0% | 0% | 0% | 5 | 0 | 0 | 612.5
2 | Generator Kama (Cons.) | G149100438 | Kama | 77 | 0 | 0 | 0 | 42.5 | 3272.5 | 0 | 0 | 0 | 0% | 0% | 0% | 5 | 0 | 0 | 385
3 | Generator Kama | XN14072430 | KDE12EW | 33 | 92 | 0 | 0 | 42.5 | 1402.5 | 3910 | 0 | 0 | 278.8% | 100% | 278.8% | 5 | 460 | 70 | 165
6 | Generatoer engine | U910518T |  | 70 | 0 | 0 | 0 | 50 | 3500 | 0 | 0 | 0 | 278.8% | 0% | 0% | 0 | 0 | 0 | 0
| Sub Total |  |  |  | 92 | 0 | 0 |  | 16381.25 | 3910 | 0 | 0 |  |  |  |  | 460 | 70 | 1162.5
6 | Welding machine ele. | 21760080016 | RDM3000K | 60 | 0 | 0 | 0 | 50 | 3000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
| HAND COMPACTORS |  |  | 60 | [8 empty] | 0% | 0% | 0% |  |  |  | 0
1 | HAND COMPACTOR | 46501133 |  | 60 | 0 | 0 | 0 | 50 | 3000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
2 | HAND COMPACTOR | PC-7229 |  | 60 | 0 | 0 | 0 | 50 | 3000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0 | #REF!
3 | HAND COMPACTOR | PC-7170 |  | 60 | 0 | 0 | 0 | 50 | 3000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
4 | HAND COMPACTOR | 46501627 |  | 60 | 0 | 0 | 0 | 50 | 3000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
|  |  |  | 240 | 0 | 0 | 0 |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total of Owned |  |  |  |  | 867.46 | 289.24 | 48.33 |  | 672345.75 | 448614.7 | 25466.34 | 3656.7 |  |  |  | 0 | 15701.24 | 15178 | 18126.5 | 3414
Rental Equipment | [18 empty] | 0
1 | Loader | 10233 | xgma | 68 | 45.49 | 0.27 | 0 | 400 | 27200 | 18196 | 108 | 0 | 66.9% | 99.41% | 67.29% | 12 | 545.88 | 591 | 816
2 | Dump Truck Rental | 3-69520 | SINOTRUCK | 68 | 52 | 1.34 | 0 | 250 | 17000 | 13000 | 335 | 0 | 76.47% | 97.49% | 78.44% | 10 | 520 | 203 | 680
3 | Dump Truck Rental | 3-69538 | SINOTRUCK | 68 | 44.29 | 0.72 | 0 | 250 | 17000 | 11072.5 | 180 | 0 | 65.13% | 98.4% | 66.19% | 10 | 442.9 | 512 | 680
4 | Dozer | 800 | CAT D8R |  | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 45 | 0 | 0 | 0
5 | Grader | 1152 | Komatsu | 70 | 42.34 | 2 | 0 | 1000 | 70000 | 42340 | 2000 | 0 | 60.49% | 95.49% | 63.34% | 18 | 762.12 | 626 | 1260
6 | BackLoader | 3613 | JCB | 56 | 55 | 0 | 0 | 400 | 22400 | 22000 | 0 | 0 | 98.21% | 100% | 98.21% | 10 | 550 | 184 | 560
6 | Dump Truck Rental | 3-58699 | SINOTRUCK |  | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 10 | 0 | 0 | 0
7 | Dump Truck Rental | 3-67361 | SINOTRUCK | 68 | 44.67 | 3.13 | 0 | 266.67 | 18133.56 | 11912.1489 | 834.6771 | 0 | 65.69% | 93.45% | 70.29% | 10 | 446.7 | 200 | 680
8 | Dump Truck Rental | 3-67362 | SINOTRUCK |  | 0 | 0 | 0 | 266.67 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 10 | 0 | 0
9 | Dump Truck Rental | 3-62628 | SINOTRUCK | 68 | 44.91 | 2.39 | 0 | 350 | 23800 | 15718.5 | 836.5 | 0 | 66.04% | 94.95% | 69.56% | 10 | 449.1 | 396
10 | Dump Truck Rental | 3-62629 | SINOTRUCK | 68 | 53.93 | 0.78 | 0 | 350 | 23800 | 18875.5 | 273 | 0 | 79.31% | 98.57% | 80.46% | 10 | 539.3 | 542
11 | Dump Truck Rental | 3-65860 | SINOTRUCK | 68 | 50 | 0 | 0 | Per KM |  |  |  |  | 73.53% | 100% | 73.53% | 10 | 500 | 321 | 680
12 | Dump Truck Rental | 3-65861 | SINOTRUCK | 68 | 50 | 0 | 0 | Per KM |  |  |  |  | 73.53% | 100% | 73.53% | 10 | 500 | 472 | 680
13 | Dump Truck Rental | 3-65862 | SINOTRUCK |  | 0 | 0 | 0 | Per KM |  |  |  |  | #DIV/0! | 0% | #DIV/0! | 10 | 0 | 0 | 0
14 | Dump Truck Rental | 3-65863 | SINOTRUCK | 68 | 50 | 0 | 0 | Per KM |  |  |  |  | 73.53% | 100% | 73.53% | 10 | 500 | 346 | 680
| Sub Total |  |  | 738 | 532.63 | 10.63 | 0 | 5183.34 | 219333.56 | 153114.6489 | 4567.1771 | 0 |  | 10.7776 |  |  | 5756 | 4393 | 6716
1 | Water Truck Rental | 17751 | FIAT | 56 | 44 | 0 | 0 | 150 | 8400 | 6600 | 0 | 0 | 78.57% | 100% | 78.57% | 10 | 440 | 200 | 560
2 | Water Truck Rental | 11302 | FIAT | 56 | 44 | 0 | 0 | 150 | 8400 | 6600 | 0 | 0 | 78.57% | 100% | 78.57% | 10 | 440 | 150 | 560
3 | Water Truck Rental | 1035 | FIAT |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 |  | 0% |  | 10 | 0 | 0 | 0
| Sub Total |  |  | 112 | 88 | 0 | 0 |  | 16800 | 13200 | 0 | 0 | 1.5714 | 2 | 1.5714 |  | 880 | 350 | 1120
1 | Cargo Truck Rental | 2351 | ISUZU | 60 | 0 | 0 | 0 | 80 | 4800 | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 |  | 0
2 | Cargo Truck Rental | 4040 | ISUZU | 60 | 0 | 0 | 0 | 80 | 4800 | 0 | 0 | 0 | 0% | 0% | 0% |  |  |  | 0
. | Sub Total |  |  | 120 | 0 | 0 | 0 | 160 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Small Vehicle rental | 10760 | 2H | 70 | 0 | 0 | 0 | 80 | 5600 | 0 | 0 | 0 | 0% | 0% | 0% | 2 | 0 | 0 | 140
2 | Small Vehicle rental | 62086 | D4D | 70 | 70 | 0 | 0 | 140 | 9800 | 9800 | 0 |  | 100% | 100% | 100% | 2 | 140 | 114 | 140 | 20596
3 | Small Vehicle rental | 49148 | Pickup | 70 | 70 | 0 | 0 | 120 | 8400 | 8400 | 0 |  | 100% | 100% | 100% | 2 | 140 | 112 | 140
4 | Small Vehicle rental | 45132 | Pickup |  |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 2 | 0 | 0 | 0
5 | Small Vehicle rental | 71685 | Hilux Pkup |  | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 2 | 0 | 0 | 0
6 | Small Vehicle Rental | 58068 | Long base |  | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 2 | 0 | 0 | 0
8 | Small Vehicle Rental | 30981 | Pickup |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 2 | 0 | 0 | 0
9 | Small Vehicle Rental | 99633 | Pickup | 70 | 70 | 0 | 0 | 120 | 8400 | 8400 | 0 | 0 | 100% | 100% | 100% | 2 | 140 | 127 | 140
10 | Small Vehicle Rental | 65025 | Long base |  | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 2 | 0 | 0 | 0
11 | Small Vehicle Rental | 60681 | Long base |  |  | 0 | 0 | 135 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 2 | 0 | 0 | 0
12 | Small Vehicle Rental | 67618 | Long base |  |  | 0 | 0 | 135 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | 2 | 0 | 0 | 0
13 | Small Vehicle Rental | 62485 | Long base | 70 | 70 | 0 | 0 | 135 | 9450 | 9450 | 0 | 0 | 100% | 100% | 100% | 2 | 140 | 113 | 140
14 | Small Vehicle Rental | 48049 | Long base | 70 | 70 | 0 | 0 | 135 | 9450 | 9450 | 0 | 0 | 100% | 100% | 100% | 2 | 140 | 141 | 140
15 | Small Vehicle Rental | 49739 | Long base | 70 | 30 | 0 | 0 | 135 | 9450 | 4050 | 0 | 0 | 42.86% | 100% | 42.86% | 2 | 60 | 68 | 140
16 | Small Vehicle Rental | G-233 | Pickup | 48 | 0 | 0 | 0 | 80 | 3840 | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0
17 | Small Vehicle Rental | code-10 | pajero | 48 | 0 | 0 | 0 | 70 | 3360 | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
18 | Small Vehicle Rental | G-29 |  | 48 | 0 | 0 | 0 | 80 | 3840 | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
19 | Small Vehicle Rental | G-00892 | SURF | 48 |  | 0 | 0 | 60 | 2880 |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
20 | Small Vehicle Rental | AFDER-086 | cobra | 48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
21 | Small Vehicle Rental | G-236 |  | 48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
22 | Small Vehicle Rental | G-66 |  | 48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
23 | Small Vehicle Rental | G-30 |  | 48 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
24 | Small Vehicle Rental | G-380 | cobra | 48 | 0 | 0 | 0 | 80 | 3840 | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
| Sub Total |  |  | 280 | 210 | 0 | 0 |  | 51100 | 49550 | 0 | 0 |  | 6 |  |  | 420 | 675 | 560
| Total of Rental |  |  | 1250 | 830.63 | 10.63 | 0 |  | 287233.56 | 215864.6489 | 4567.1771 | 0 |  |  |  |  | 7056 | 5418 | 8396 | 1276

## Weekly Progress Report
Cross-land Construction Company
Project: Haro sebu-Lelo-Qaqe
Weekly Progress Report
Week 32 ((23-29)-08-07)
NO. | DESCREPTION | Unit | Unit Price | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Tursday | Adjusted Plan |  | Executed
|  |  |  | Day-1 23/08/07 | Day-2 24/08/07 | Day-3 25/08/07 | Day-4 26/08/07 | Day-5 27/08/07 | Day-6 28/08/07 | Day-7 29/08/07 | Qty. | Amount | Qty. | Amount
GR.2. EARTH WORK
1 | General | ls | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2750 | 0 | 2750
2 | Clearing & Grubbing | ha | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Subgrade Preparation | M3 | 20 | 220 | 1125 | 0 | 545 | 200 | 0 | 125 | 2325.75 | 46515 | 2215 | 44300
3 | Embankment/borrow Placing | m3 | 34.71 | 650 | 0 | 0 | 0 | 0 | 0 | 458 | 1218.8 | 42304.548 | 1108 | 38458.68
4 | Extra over itemm 42.01 for common(Normal)excavation to spoil | m3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
4 | Fine Grading by embankment/borrow | m3 | 13.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
5 | Capping Placing(G20) | m3 | 46.8 | 0 | 0 | 0 | 0 | 297 | 0 | 0 | 326.7 | 15289.56 | 297 | 13899.6
6 | Fine Grading-Capping(G20) | m3 | 5.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
7 | Capping Placing(G7) | m3 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 460 | 21160 | 400 | 18400
8 | Fine Grading-Capping(G7) | m3 | 5.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
42.03(a) | Cut to spoil |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
1 | Extra over itemm 42.01 for common(Normal)excavation to spoil | m3 | 88 | 2755 | 2350 | 0 | 2352 | 1545 | 1690 | 1585 | 22281 | 1960728 | 12277 | 1080376
2 | Extra over itemm 42.01 for intermediate materials excavation to spoil | m3 | 99 | 0 | 300 | 0 | 300 | 160 | 160 | 100 |  | 0 | 1020 | 100980
3 | Extra over itemm 42.01 for excavating and breaking in rock(hard material)excavation to spoil | m3 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Sub Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2088747.108 | 0 | 1299164.28
GR.3.PAVEMENT Work(Placing) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
54.01(a) | Subbase Placing |  | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Sub Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
GR.4.MINOR DRAINAGE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1 | Structural excavation(Common) | m3 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
2 | Structural excavation(moderate) | m3 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
3 | Structural excavation(Hard) | m3 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
4 | Backfilling from excavated material | m3 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
5 | Backfilling(Selected)Minor | m3 | 47.5 | 0 | 0 | 0 | 12.49 | 7.65 | 0 | 18.36 | 42.35 | 2011.625 | 38.5 | 1828.75
6 | Installation and curing(dia.36") | lm | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Installation and curing(dia.42") | lm | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
8 | Installation and curing(dia.48") | lm | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
9 | Class A Concrete ( Minor ) | m3 | 2524.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
10 | Rebar bending & Placing | Kg | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
11 | Masonory construction | m3 | 967.6584 | 12.05 | 11.24 | 0 | 11.22 | 5.5 | 0 | 5.5 | 74.1 | 71703.4877 | 45.51 | 44038.134
12 | Paved construction | m2 | 89.8603 | 16 | 12.6 | 0 | 0 | 0 | 0 | 57 | 110 | 9884.6307 | 85.6 | 7692.0399
Sub Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 83599.7435 | 0 | 53558.9239
GR.5.MAJOR DRAINAGE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1 | Excavation of soft material irrespective of depth | m3 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Excavation of intermidiate material irrespective of depth | m3 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
3 | Excavation of Hard material irrespective of depth | m3 | 500 | 79.29 | 48.3 | 0 | 80.5 | 10.35 | 0 | 78 | 355.728 | 177864 | 296.44 | 148220
4 | Backfilling from excavated material | m3 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
5 | Handlaid filling | m3 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
6 | Granular material filling | m3 | 106.4 | 0 | 0 | 0 | 120 | 24 | 0 | 0 |  | 0 | 144 | 15321.6
7 | Concrete Class ''A'' | m3 | 3832.4205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Concrete C-25 | Kg | 4900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
9 | Concrete C-20 | LM | 20.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
10 | Concrete C-15 | m3 | 89.2958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
11 | Concrete C-5 | m3 | 2912.6396 | 0 | 0 | 0 | 0 | 4.24 | 0 | 1.56 | 5.8 | 16893.3095 | 5.8 | 16893.3095
12 | Rebar bending & Placing | Kg | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
13 | Concrete bridge railing with R.C posts | LM | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
14 | Masonory construction | m3 | 1064.8335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 194757.3095 | 0 | 180434.9095
GR.6.Retaing wall and Mis. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
1 | Reflective road sign | pcs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
2 | Project sign with post | pcs | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
3 | Concrete sign post | pcs | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Sub Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Cummulative |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | 0
MATERIAL PRODUCTION |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1 | Excavation to stock/production | m3 | 22.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
3 | Capping Production(G20) | m3 | 29.25 | 0 | 0 | 0 | 250 | 335 | 0 | 375 | 1056 | 30888 | 960 | 28080
5 | Capping Production(G7) | m3 | 28.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
5 | Subbase production (Natural) | m3 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
6 | Backfill Material Production(minor) | m3 | 31.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
7 | R.C. Pipe Production(dia.36") | Pcs | 4005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
8 | R.C. Pipe Production(dia.42") | Pcs | 4806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
8 | R.C. Pipe Production(dia.48") | Pcs | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'A' Concrete(Minor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
9 | Sand production | m3 | 16.7813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
10 | Stone Production ( For Aggregate by Quarryman ) | m3 | 75.053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
11 | Stone Production | m3 | 47.6078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
12 | C.agg. production | M3 | 229.792 | 0 | 4.64 | 0 | 5.04 | 5.808 | 4.464 | 7.68 | 31.12 | 7151.1276 | 27.632 | 6349.613
| Class 'C' Concrete(Minor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
13 | Sand production | m3 | 16.0963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
14 | Stone Production ( For Aggregate by Quarryman ) | m3 | 71.9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
15 | Stone Production | m3 | 45.6646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
16 | C.agg. production | m3 | 220.4128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'A' Concrete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
17 | Sand production |  | 20.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
18 | Stone Production ( For Aggregate by Quarryman ) | m3 | 92.3723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
19 | Stone Production | m3 | 58.5938 | 0 | 0 | 0 | 32 | 32 | 24 | 0 | 96.8 | 5671.8752 | 88 | 5156.2502
20 | C.agg. production | m3 | 282.8188 | 0 | 2.6 | 0 | 4.26 | 4.952 | 4.056 | 5.64 | 22.63 | 6400.1897 | 21.508 | 6082.867
| Class 'C-25' Concrete | m3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
21 | Sand production | Lm | 20.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
22 | Stone Production ( For Aggregate by Quarryman ) | Lm | 90.5248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
23 | Stone Production | 0 | 57.4219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
24 | C.agg. production | m3 | 277.1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'C-20' Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
25 | Sand production | m3 | 19.8275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
26 | Stone Production ( For Aggregate by Quarryman ) | m3 | 88.6774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
27 | Stone Production | m3 | 56.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
28 | C.agg. production | m3 | 271.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'C-15' Concrete | m3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
29 | Sand production | Lm | 16.523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
30 | Stone Production ( For Aggregate by Quarryman ) | Lm | 73.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
31 | Stone Production | m3 | 46.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
32 | C.agg. production | m3 | 226.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'C-5' Concrete | m3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
33 | Sand production | m3 | 15.6968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
34 | Stone Production ( For Aggregate by Quarryman ) | m3 | 70.2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
35 | Stone Production | m3 | 44.5313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
36 | C.agg. production | m3 | 214.9423 | 0 | 1.8 | 0 | 3.9 | 4.08 | 3.6 | 4.62 | 19.56 | 4204.2713 | 18 | 3868.9613
| Class 'B' masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
38 | Stone Production by Excavator ( For Masonary ) | m3 | 59.8224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Stone prodn. (Q.man) | m3 | 120.3979 | 5.69 | 4.32 | 0 | 5.76 | 7.2 | 0 | 0 | 26.36 | 3173.6874 | 22.97 | 2765.5387
40 | Sand production | m3 | 14.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| G.R. paved water way(Paved Ditch) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
41 | Stone Production by Excavator ( For Masonary ) | m3 | 15.1032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
42 | Stone prodn. (Q.man) | m3 | 30.3966 | 0 | 6.48 | 0 | 10.8 | 0 | 0 | 1.8 | 20.988 | 637.9643 | 19.08 | 579.9675
43 | Sand production | m3 | 6.0291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Production of major backfill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
44 | Granular material production (Natural) | m3 | 30.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
45 | Handlaid Material Production | m3 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Sub Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 58127.1154 | 0 | 52883.1977
Material Hauling |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1 | Embankment/borrow Hauling | m3 | 18.69 | 156 | 144 | 0 | 0 | 276 | 0 | 372 | 1090.2 | 20375.838 | 948 | 17718.12
2 | Capping Hauling-Capping(G20) | m3 | 35.1 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 528 | 18532.8 | 480 | 16848
3 | Capping Hauling-Capping(G7) | m3 | 34.5 | 0 | 0 | 0 | 204 | 60 | 0 | 216 | 528 | 18216 | 480 | 16560
4 | Subbase Hauling | m3 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
5 | Backfill material Hauling(Minor) | m3 | 46.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
6 | Pipe hauling(dia.36") | Lm | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
7 | Pipe hauling(dia.42") | Lm | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
8 | Pipe hauling(dia.48") | Lm | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'A' Concrete(Minor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
9 | Sand hauling | m3 | 74.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Stone hauling to crusher | m3 | 86.5541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
11 | C. agg. Hualing | m3 | 316.3329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'C' Concrete(Minor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
12 | Sand hauling | m3 | 71.0123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
13 | Stone hauling to crusher | m3 | 83.0213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
14 | C. agg. Hualing | m3 | 303.4213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'A' Concrete | m3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
15 | Sand hauling | m3 | 91.1182 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 1093.4184 | 12 | 1093.4184
16 | Stone hauling to crusher | m3 | 106.5273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
17 | C. agg. Hualing | m3 | 389.3298 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 4671.9576 | 12 | 4671.9576
| Class 'C-25' Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
18 | Sand hauling | m3 | 89.2958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
19 | Stone hauling to crusher | m2 | 104.3968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
20 | C. agg. Hualing | m2 | 381.5432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'C-20' Concrete | m2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
21 | Sand hauling | m3 | 87.4735 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 1049.6816 | 12 | 1049.6816
22 | Stone hauling to crusher | m3 | 102.2663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
23 | C. agg. Hualing | m3 | 373.7566 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4485.0793 | 12 | 4485.0793
| Class 'C-15' Concrete | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
24 | Sand hauling | m3 | 72.8946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
25 | Stone hauling to crusher | km | 85.2219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
26 | C. agg. Hualing | m3 | 311.4638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'C-5' Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
27 | Sand hauling | m3 | 69.2498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
28 | Stone hauling to crusher | m3 | 80.9608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
29 | C. agg. Hualing | m3 | 295.8906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Class 'B' masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
30 | Stone hauling | m3 | 522.8862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Sand hauling | m3 | 105.3546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| G.R. paved water way(Paved Ditch) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
32 | Stone hauling | m3 | 132.0121 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 96 | 12673.1605 | 96 | 12673.1605
33 | Sand hauling | m3 | 26.5987 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 319.184 | 12 | 319.184
| Hauling of major backfill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
34 | Granular material Hauling | m3 | 53.2 | 0 | 0 | 0 | 120 | 24 | 0 | 0 | 144 | 7660.8 | 144 | 7660.8
35 | Handlaid material Hauling | m3 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Sub Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 89077.9194 | 0 | 83079.4014
| Form work |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1 | Rebar bending & Placing | m2 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
2 | Form work(Major) | m2 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
3 | Falsework | m2 | 126.1656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Sub Total | [10 empty] | 0 | 0 | 0
Grand Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2514309.1959 | 0 | 1669120.7125
UNPAID ITEMS
Pond Construction |  | M2 | 0
Camp construction |  | % | 0
Service road |  | km | 0
Dumping for Detour |  | m3 | 0
Placing for Detour |  | m3 | 0

## Summary
Cross-land Construction Company | [12 empty] | Week No: 22 |  |  |  |  | FUEL |  |  | Lubrelicant(OWN) | [5 empty] | Fuel own | [9 empty] | Lubrelicant
Project: Haro sebu-Lelo-Qaqe | [12 empty] | 01/11/2008 - 07/11/2008 |  |  | project current week | Own fuel | 11.65 | 15178 | 176823.7 | 15w40 | 32.0025 | 26 | 832.065 |  |  | Equipment | No of Equi. | Op.h |  |  | p/h | Nafta
[17 empty] | Rental fuel | 11.65 | 5418 | 63119.7 | Senthiese | 1453.2 |  | 0
[6 empty] | Week 32 ((23-29)-08-07) | [9 empty] | previous week |  | 13 |  | 0 | 10w | 23.855 | 33 | 787.215 |  |  | Dozer | 5 | 8 | 6 | 240 | 45 | 10800 | 103140 | 850 | 204000
DATE | FUEL (lit) |  | LUBRICANT |  | CONSTRUCTION (Birr) |  |  | TYER AND Tube | SPARE PART | MANPOWER |  | EQUIPMENT |  | GENERAL ITEM | [5 empty] | 239943.4 | HP22 | 28.27 |  | 0 |  |  | Grader | 5 | 8 | 6 | 240 | 18 | 4320 | 41256 | 550 | 132000
| OWN | RENTAL | OWN | RENTAL | Construction Materials |  | CAMP CONSTRUCTION(Consultant) |  |  | BASIC | OVERTIME | OWN | RENTAL |  |  |  |  | Cement |  |  | HD50 | 19.98 |  | 0 |  | 0 | Smooth roller | 3 | 1 | 6 | 18 | 8 | 144 | 1375.2 | 280 | 5040
Day-1 23/08/07 | 2870 | 1194 |  |  | Camp Construction | [11 empty] | Messobo | 106.906 |  | 0 | 85W90 | 19.61 |  | 0 |  |  | Smooth roller |  |  |  | 0 |  | 0 | 0 | 280 | 0
Day-2 24/08/07 | 3182 | 1438 |  |  | Cement | [11 empty] | Mugger( opc) | 108.7115 |  | 0 | 85W140 | 19.5227 |  | 0 |  |  | Loader | 3 | 8 | 6 | 144 | 18 | 2592 | 24753.6 | 450 | 64800
Day-3 25/08/07 | 0 | 0 |  |  | OPC | 0 | [10 empty] | Barzaf | 1194 |  | 0 | B/Fluid 424 | 69.785 | 3 | 209.355
Day-4 26/08/07 | 3014 | 945 |  |  | PPC | 33660 | [11 empty] | Maximum Spare |  |  | Grease 30722 | 28.26 |  | 0 |  |  | Excavator | 2 | 8 | 6 | 96 | 18 | 1728 | 16502.4 | 550 | 52800
Day-5 27/08/07 | 2058 | 1027 |  |  | River Sand | 3600 | [10 empty] | Motor Lp | 22011.53 |  | 0 | DTE-26 | 13.17 |  | 0 |  |  | Crusher | 1 | 8 | 6 | 48 | 2 | 96 | 916.8 | 50 | 2400
Day-6 28/08/07 | 1707 | 388 |  |  | Rebar Dai.32=54 Berga | 88963.92 | [10 empty] | cutting edge | 2130.95 |  | 0 | 15w40 Shell | 20.3 |  | 0 |  |  | Water Pump | 5 | 4 | 6 | 120 | 0.5 | 60 | 573 | 5 | 600
Day-7 29/08/07 | 2347 | 426
[17 empty] | Tyre 11*20 | 2826.09 |  | 0 | DTE-25 | 14.374 |  | 0 |  |  | Robin Vibrator | 6 | 8 | 6 | 288 | 0.5 | 144 | 1375.2 | 5 | 1440
WEEKLY | 15178 | 5418 | 0 | 0 |  | 126223.92 | 0 | #REF! | #REF! |  |  | 444704.7 | 272035.032 | 0 |  |  | Tube | 1648.7 |  | 0 | ATX | 26.5013 |  | 0 |  |  | Dump truck | 11 | 8 | 6 | 528 | 10 | 5280 | 50424 | 120 | 63360
Prepared By_________________ |  | Checked By_____________________ |  |  | Approved By___________________
FASIL N. |  | Natan K. |  |  | AMARE M.
Cross-land Construction Company | [8 empty] | 72661 | [11 empty] | SAE-50 | 46.0903 | 7 | 322.6321 | [9 empty] | 0
Project: Haro sebu-Lelo-Qaqe | [7 empty] | 20596 | [12 empty] | 80W90 | 26.265 |  | 0 | [9 empty] | 0
[8 empty] | 20596 | 47.6962 | [5 empty] | 2472 | [5 empty] | A3-68 | 24.335 |  | 0
Weekly Income Expense summary | [8 empty] | 108.0506 | [11 empty] | A3-46 | 24.335 |  | 0 |  |  | Air compressor | 1 | 8 | 6 | 48 | 15 | 720 | 6876 | 5 | 240
[6 empty] | Week 32 ((23-29)-08-07) |  |  | 94.8101 | [7 empty] | Rebar(24) | 608.7 |  | 0 | Benzin | 10.5 |  | 0 |  |  | Shower truck own | 12 | 8 | 6 | 576 | 10 | 5760 | 55008 | 66.6667 | 38400
NO | DESCRIPTION | EXPENSE |  | DESCRIPTION |  | INCOME |  |  | 0 | [7 empty] | Rebar(16) | 600 |  | 0 | AC50 | 33.405 |  | 0 |  |  | Small Vehicle | 7 | 8 | 6 | 336 | 3 | 1008 | 9626.4 | 50 | 16800
|  | PLAN | ACTUAL |  |  | PLAN | ACTUAL | 15178 | 0 | [7 empty] | Rebar(12) | 573.3 |  | 0 | Ep 3 | 41.14 |  | 0 |  |  | Fuel truck | 3 | 8 | 6 | 144 | 10 | 1440 | 13752 | 80 | 11520
| MANPOWER | 270596.7339 | 265675.57 | BILL NO.1: GENERAL |  | 2750 | 2750 | 5418 | 244705.08 | 20970.49 | 334180 | -331430 |  |  |  |  | Rebar(6) | 1100 |  | 0 | Az011068 | 24.335 |  | 0 |  |  | Generator | 7 | 8 | 6 | 336 | 5 | 1680 | 16044 | 2 | 672
2.1 | PERMANENT EMPLOYEES | 166158.2489 | 163678.57 | BILL NO.2: SITE CLEARANCE |  | 0 | 0 |  | 197309.73 |  | 55200 | -55200 | -386630 |  |  |  | C I S | 74.09 |  | 0 | Ep 2 | 41.387 | 35 | 1448.545 |  |  | MIXER | 3 | 8 | 6 | 144 | 2 | 288 | 2750.4 | 20 | 2880
[21 empty] | R .Collent(26 c) | 41.06 |  | 0
| Basic Salary | [6 empty] | 165436.54 | [12 empty] | 454 | 60.45 |  | 0
A | Basic Salary | 71093.1425 | 70389.25 | BILL NO.3: DRAINAGE |  | 83599.7435 | 53558.9239 | 23633.7914 | 71850 |  | 0 | 53558.9239 |  |  |  |  | C I S | 48.7 |  | 0 | Gx90 | 16.67 |  | 0 |  |  | Cargo truck | 3 | 8 | 6 | 144 | 10 | 1440 | 13752 | 120 | 17280
B | Responsibility Allowance | 4500 | 4500 | BILL NO.4: EARTH WORKS |  | 2085997.108 | 1296414.28 |  | 5500 |  | 815951.2536 | 480463.0264 | -469236.4531 |  |  |  |  | TOTAL |  | 0 |  |  |  | 3599.8121
C | Hardship Allowance | 0 |  | BILL NO.5: SUB BASE,ROADBASE&GRAVEL WEARING COARSE |  | 0 | 0 |  | 27815 |  | 0 | 0
D | Perdiem | 53442.9 | 52395 | BILL NO.8: STRUCTURES |  | 194757.3095 | 180434.9095 |  | 1250 |  | 0 | 180434.9095 | [21 empty] | 0
E | Special Allowance | 0 |  | BILL NO.9: ANCILLARY WORKS |  | 0 | 0 |  | 52625 |  | 0 | 0 | [8 empty] | Lubrelicant(RENTAL)
F | Over Time | 29224.53 | 28651.5 | PRODUCTION INCOME |  | 58127.1154 | 52883.1977 |  | 38269.73 |  | 705549.2579 | -652666.0602 | [8 empty] | 15w40 | 32.0025 |  | 0
G | Pension | 7897.6764 | 7742.82
2.1.2 | TEMPORARY EMPLOYEES | 104438.485 | 101997 | HAULING INCOME |  | 89077.9194 | 83079.4014 |  | 47395.35 |  | 560547.7302 | -477468.3288 | [8 empty] | Senthiese | 1453.2 |  | 0
A | Basic Salary | 63079.35 | 61842.5 | [5 empty] | 28320 |  |  | -802307.5292 | [8 empty] | 10w | 23.855 |  | 0
F | Over Time | 41359.135 | 40154.5 | [5 empty] | 19075.35 | [11 empty] | B/Fluid 424 | 69.785 |  | 0
2.2 | EQUIPMENT | 996817.656 | 716739.732 | [5 empty] | 835061.5017 | -118321.7697 | [10 empty] | Grease 30722 | 28.26 |  | 0
2.2.1 | OWN | 712232 | 444704.7 | [5 empty] | 516890.055 | -72185.355 | [10 empty] | DTE-26 | 13.17 |  | 0
A | Heavy Duty | 645660 | 392157.7 | [5 empty] | 433233.255 | [11 empty] | 15w40 Shell | 20.3 |  | 0
B | Trucks | 29682 | 28747 | [5 empty] | 55746 | [11 empty] | DTE-25 | 14.374 |  | 0
C | Vehicle | 8330 | 8330 | [5 empty] | 8400 | [11 empty] | ATX | 26.5013 |  | 0
D | Crusher Plant | 28560 | 15470 | [5 empty] | 2981.55
E | Auxillary | 0 | [6 empty] | 16529.25 | 0 | [10 empty] | 80W90 | 26.265 |  |  | 5 | [7 empty] | 37500 | 358125 | Own | 460674 | 4606.74
2.2.2 | RENTAL | 284585.656 | 272035.032 | [5 empty] | 318171.4467 | -46136.4147 | [24 empty] | Rental | 0
A | Heavy Duty | 119600 | 84644 | [5 empty] | 67595 | [6 empty] | WEEKLY RENTAL EQUIPMENTS COST |  |  |  |  | KEROSINE | 5.75 |  | 0 | [5 empty] | Fuel rental | [9 empty] | Lubrelicant
B | Trucks | 50800 | 85269.652 |  |  |  |  | 59660 | 189626.4467 | [6 empty] | ___SURVEYING |  |  |  |  | Benzin | 10.5 |  | 0 | [5 empty] | Equipment | No of Equi. | Op.h | No of Days In A Week | Total hrs. in a week | p/h | Nafta | Total Fuel Cost | Rental Reate | Total Rent Cost
C | Vehicle | 51100 | 49550 | [5 empty] | 60950 | [6 empty] | __TOTAL STATION=350*7=2450 |  |  |  |  | AC50 | 33.405 |  | 0
D | Crusher Plant | [14 empty] | ___ | ___OTHERS=902*7=6314 |  |  |  | Ep 3 | 41.14 |  | 0 | [5 empty] | Dozer |  | 8 | 6 | 0 | 45 | 0 | 0 | 850 | 0
E | Dump Trucks Per Km | 63085.656 | 52571.38 | [5 empty] | 1.0345 | [6 empty] | ____LAB.EQTS =404.8*7=2833.60 |  |  |  |  | Az011068 | 24.335 |  | 0 | [5 empty] | Grader |  | 8 | 6 | 0 | 18 | 0 | 0 | 550 | 0
2.3 | SPARE PART, TYRE& TUBE | 0 | 0 | [5 empty] | 88557.1105 | -88557.1105 | [10 empty] | Ep 2 | 41.387 |  | 0 |  |  | 2450 |  |  | Smooth roller | 1 | 1 | 6 | 6 | 8 | 48 | 458.4 | 280 | 1680
A | Spare Part | 0 | [6 empty] | 52789.2205 | [7 empty] | 2450 |  |  |  | Gx90 | 16.67 |  | 0 |  |  | 6314 |  |  | Small Vehicle | 18 | 8 | 6 | 864 | 3 | 2592 | 24753.6 | 50 | 43200
B | Tyre & Tube | 0 | [6 empty] | 35767.89 | [7 empty] | 6314 | [6 empty] | 0 |  |  | 2833.6 |  |  | Loader | 1 | 8 | 6 | 48 | 18 | 864 | 8251.2 | 450 | 21600
2.4 | FUEL | 399532.2392 | 341481.68 | [5 empty] | 363797.7 | -22316.02 | [6 empty] | 2833.6 | [12 empty] | Air compressor |  | 8 | 6 | 0 | 15 | 0 | 0 | 5 | 0
A | Own | 260326.5592 | 251651.24 | [5 empty] | 229496.05 | [7 empty] | 11597.6 | [12 empty] | Excavator |  | 8 | 6 | 0 | 18 | 0 | 0 | 550 | 0
B | Rental | 139205.68 | 89830.44 | [5 empty] | 134301.65 | [20 empty] | Crusher |  | 8 | 6 | 0 | 2 | 0 | 0 | 50 | 0
2.5 | LUBRICANT (Engine Oil(15 W40,Grease ,10W, 85w140,Battery Water & Benzene) | 56487.343 | 51352.13 | [5 empty] | 1623.915 | 49728.215 | [19 empty] | Water Pump |  | 4 | 6 | 0 | 0.5 | 0 | 0 | 5 | 0
A | Own | 50068.018 | 45516.38 | [5 empty] | 1623.915 | [20 empty] | Robin Vibrator |  | 8 | 6 | 0 | 0.5 | 0 | 0 | 5 | 0
B | Rental | 6419.325 | 5835.75 | [5 empty] | 0 | [20 empty] | Dump truck | 10 | 8 | 6 | 480 | 10 | 4800 | 45840 | 160 | 76800
2.6 | CONSTRUCTION MATERIAL | 138846.312 | 126223.92 | [5 empty] | 16817.6 | 109406.32 | [19 empty] | Shower truck own |  | 8 | 6 | 0 | 10 | 0 | 0 | 66.6667 | 0
A | Main Road | 138846.312 | 126223.92 | [5 empty] | 0 | [20 empty] | Cargo truck | 3 | 8 | 6 | 144 | 10 | 1440 | 13752 | 120 | 17280
B | Camp Construction | 0 | [6 empty] | 16817.6 | [27 empty] | 0
| 1)Contractor | 0 | 0 | [5 empty] | 16817.6 |  | 1175000% | [25 empty] | 0
| 2)Consultant | [7 empty] | 0 | [27 empty] | 0
2.7 | General items | 15309.75 | 13847.5 | [5 empty] | 26281.98 | -12434.48 | [26 empty] | 0
|  | 0 | [6 empty] | 3478.98 | [27 empty] | 0
| Laboratory Test | 1980 | 1800 | [5 empty] | 6992 | -5192 | [26 empty] | 0
| Perdium | 1782.5 | 1550
| Rental Driver Over Time | 1954.15 | 1776.5 | [5 empty] | 811 | 965.5 | [26 empty] | 0
| Consultant Allowance(Over time) | 9043.1 | 8221 | [5 empty] | 15000 | [27 empty] | 0
| Other Labour Cost | 550 | 500 | [26 empty] | Generator |  | 8 | 6 | 0 | 5 | 0 | 0 | 2 | 0
| Total | 1877590.0341 | 1515320.532 |  |  | 2514309.1959 | 1669120.7125 |  | 1576844.8872 | -61524.3552 | [19 empty] | MIXER |  | 8 | 6 | 0 | 2 | 0 | 0 | 20 | 0
DIRECT COST |  |  | Plan by Direct cost |  | Actual by Direct cost | [31 empty] | 0
|  |  | #REF! |  | #REF! | [24 empty] | Fuel truck |  | 8 | 6 | 0 | 4 | 0 | 0 | 66.6667 | 0
0
Prepared By ______________________ |  |  | Checked By _____________________ |  |  | Approved By _____________________ | [23 empty] | Shower truck |  | 8 | 6 | 0 | 6 | 0 | 0 | 66.6667 | 0
[30 empty] | Total | [6 empty] | 93055.2 |  | 120420 | 1204.2
|  | 271952.2 |  |  | 852260.4017 | -903210.3364 | 2367580.9337
2094327.2378
|  | plan(income-expense) | 636719.1618 | Actual(income-expense) | 153800.1805 |  |  |  | 2080000%
890941.8173
2040230.9337
6210
—
13050
Prepared By______________________
FASIL N.
49 |  |  |  |  | Checked By_______________________ |  |  |  | Plan Income |  |  |  |  | Actual Income
[6 empty] | Natan K. |  |  | 2514309.1959 |  |  |  |  | 1669120.7125
Approved By_______________________
AMARE M.
74459
|  |  | 1.5406 | 0.64908
149465.601
63181.37

## Summary (new)2 (hidden)
Cross-land Construction Company | [12 empty] | Week No: 22 |  |  |  |  | FUEL |  |  | Lubrelicant(OWN) | [5 empty] | Fuel own | [9 empty] | Lubrelicant
Project: Haro sebu-Lelo-Qaqe | [12 empty] | 01/11/2008 - 07/11/2008 |  |  | project current week | Own fuel | 11.65 | 11764 | 137050.6 | 15w40 | 32.0025 | 26 | 832.065 |  |  | Equipment | No of Equi. | Op.h |  |  | p/h | Nafta
[17 empty] | Rental fuel | 11.65 | 4142 | 48254.3 | Senthiese | 1453.2 |  | 0
[6 empty] | Week 32 ((23-29)-08-07) | [9 empty] | previous week |  | 13 |  | 0 | 10w | 23.855 | 33 | 787.215 |  |  | Dozer | 5 | 8 | 6 | 240 | 45 | 10800 | 103140 | 850 | 204000
DATE | FUEL (lit) |  | LUBRICANT |  | CONSTRUCTION (Birr) |  |  | TYER AND Tube | SPARE PART | MANPOWER |  | EQUIPMENT |  | GENERAL ITEM | [5 empty] | 185304.9 | HP22 | 28.27 |  | 0 |  |  | Grader | 5 | 8 | 6 | 240 | 18 | 4320 | 41256 | 550 | 132000
| OWN | RENTAL | OWN | RENTAL | Construction Materials |  | CAMP CONSTRUCTION(Consultant) |  |  | BASIC | OVERTIME | OWN | RENTAL |  |  |  |  | Cement |  |  | HD50 | 19.98 |  | 0 |  | 0 | Smooth roller | 3 | 1 | 6 | 18 | 8 | 144 | 1375.2 | 280 | 5040
Day-1 11/07/07 | 0 | 0 |  |  | Camp Construction | [11 empty] | Messobo | 106.906 |  | 0 | 85W90 | 19.61 |  | 0 |  |  | Smooth roller |  |  |  | 0 |  | 0 | 0 | 280 | 0
Day-2 24/08/07 | 3182 | 1438 |  |  | Cement | [11 empty] | Mugger( opc) | 108.7115 |  | 0 | 85W140 | 19.5227 |  | 0 |  |  | Loader | 3 | 8 | 6 | 144 | 18 | 2592 | 24753.6 | 450 | 64800
Day-3 25/08/07 | 0 | 0 |  |  | OPC | 0 | [10 empty] | Barzaf | 1194 |  | 0 | B/Fluid 424 | 69.785 | 3 | 209.355
Day-4 14/06/07 | 2470 | 863 |  |  | PPC | 21738.75 | [11 empty] | Maximum Spare |  |  | Grease 30722 | 28.26 |  | 0 |  |  | Excavator | 2 | 8 | 6 | 96 | 18 | 1728 | 16502.4 | 550 | 52800
Day-5 27/08/07 | 2058 | 1027 |  |  | River Sand | 22500 | [10 empty] | Motor Lp | 22011.53 |  | 0 | DTE-26 | 13.17 |  | 0 |  |  | Crusher | 1 | 8 | 6 | 48 | 2 | 96 | 916.8 | 50 | 2400
Day-6 28/08/07 | 1707 | 388 | [14 empty] | cutting edge | 2130.95 |  | 0 | 15w40 Shell | 20.3 |  | 0 |  |  | Water Pump | 5 | 4 | 6 | 120 | 0.5 | 60 | 573 | 5 | 600
Day-7 29/08/07 | 2347 | 426
[17 empty] | Tyre 11*20 | 2826.09 |  | 0 | DTE-25 | 14.374 |  | 0 |  |  | Robin Vibrator | 6 | 8 | 6 | 288 | 0.5 | 144 | 1375.2 | 5 | 1440
WEEKLY | 11764 | 4142 | 0 |  |  | 44238.75 | 0 | #REF! | #REF! |  |  | 434504.7 | 278570.212 | 0 |  |  | Tube | 1648.7 |  | 0 | ATX | 26.5013 |  | 0 |  |  | Dump truck | 11 | 8 | 6 | 528 | 10 | 5280 | 50424 | 120 | 63360
Prepared By_________________ |  | Checked By_____________________ |  |  | Approved By___________________
Fasil N. |  | Natan K. |  |  | ABEL N.
Cross-land Construction Company | [8 empty] | 72661 | [11 empty] | SAE-50 | 46.0903 | 7 | 322.6321 | [9 empty] | 0
Project: Haro sebu-Lelo-Qaqe | [7 empty] | 15906 | [12 empty] | 80W90 | 26.265 |  | 0 | [9 empty] | 0
[8 empty] | 15906 | 47.6962 | [5 empty] | 2472 | [5 empty] | A3-68 | 24.335 |  | 0
Weekly Income Expense summary | [8 empty] | 108.0506 | [11 empty] | A3-46 | 24.335 |  | 0 |  |  | Air compressor | 1 | 8 | 6 | 48 | 15 | 720 | 6876 | 5 | 240
[6 empty] | Week 32 ((23-29)-08-07) |  |  | 94.8101 | [7 empty] | Rebar(24) | 608.7 |  | 0 | Benzin | 10.5 |  | 0 |  |  | Shower truck own | 12 | 8 | 6 | 576 | 10 | 5760 | 55008 | 66.6667 | 38400
NO | DESCRIPTION | EXPENSE |  | DESCRIPTION |  | INCOME |  |  | 0 | [7 empty] | Rebar(16) | 600 |  | 0 | AC50 | 33.405 |  | 0 |  |  | Small Vehicle | 7 | 8 | 6 | 336 | 3 | 1008 | 9626.4 | 50 | 16800
|  | PLAN | ACTUAL |  |  | PLAN | ACTUAL | 11764 | 0 | [7 empty] | Rebar(12) | 573.3 |  | 0 | Ep 3 | 41.14 |  | 0 |  |  | Fuel truck | 3 | 8 | 6 | 144 | 10 | 1440 | 13752 | 80 | 11520
| MANPOWER | 283309.8741 | 278215.97 | BILL NO.1: GENERAL |  | 2750 | 2750 | 4142 | 244705.08 | 33510.89 | 334180 | -331430 |  |  |  |  | Rebar(6) | 1100 |  | 0 | Az011068 | 24.335 |  | 0 |  |  | Generator | 7 | 8 | 6 | 336 | 5 | 1680 | 16044 | 2 | 672
2.1 | PERMANENT EMPLOYEES | 177601.0218 | 174942.08 | BILL NO.2: SITE CLEARANCE |  | 0 | 0 |  | 197309.73 |  | 55200 | -55200 | -386630 |  |  |  | C I S | 74.09 |  | 0 | Ep 2 | 41.387 | 35 | 1448.545 |  |  | MIXER | 3 | 8 | 6 | 144 | 2 | 288 | 2750.4 | 20 | 2880
[21 empty] | R .Collent(26 c) | 41.06 |  | 0
| Basic Salary | [6 empty] | 152227.614 | [12 empty] | 454 | 60.45 |  | 0
A | Basic Salary | 75234.8798 | 74489.98 | BILL NO.3: DRAINAGE |  | 83599.7435 | 53558.9239 | 21746.802 | 71850 |  | 0 | 53558.9239 |  |  |  |  | C I S | 48.7 |  | 0 | Gx90 | 16.67 |  | 0 |  |  | Cargo truck | 3 | 8 | 6 | 144 | 10 | 1440 | 13752 | 120 | 17280
B | Responsibility Allowance | 4750 | 4750 | BILL NO.4: EARTH WORKS |  | 2085997.108 | 1296414.28 |  | 5500 |  | 815951.2536 | 480463.0264 | -469236.4531 |  |  |  |  | TOTAL |  | 0 |  |  |  | 3599.8121
C | Hardship Allowance | 0 |  | BILL NO.5: SUB BASE,ROADBASE&GRAVEL WEARING COARSE |  | 0 | 0 |  | 27815 |  | 0 | 0
D | Perdiem | 53503.08 | 52454 | BILL NO.8: STRUCTURES |  | 194757.3095 | 180434.9095 |  | 1250 |  | 0 | 180434.9095 | [21 empty] | 0
E | Special Allowance | 0 |  | BILL NO.9: ANCILLARY WORKS |  | 0 | 0 |  | 52625 |  | 0 | 0 | [8 empty] | Lubrelicant(RENTAL)
F | Over Time | 35755.284 | 35054.2 | PRODUCTION INCOME |  | 58127.1154 | 52883.1977 |  | 38269.73 |  | 705549.2579 | -652666.0602 | [8 empty] | 15w40 | 32.0025 |  | 0
G | Pension | 8357.778 | 8193.9
2.1.2 | TEMPORARY EMPLOYEES | 105708.8523 | 103273.89 | HAULING INCOME |  | 89077.9194 | 83079.4014 |  | 47395.35 |  | 560547.7302 | -477468.3288 | [8 empty] | Senthiese | 1453.2 |  | 0
A | Basic Salary | 67651.9488 | 66325.44 | [5 empty] | 28320 |  |  | -802307.5292 | [8 empty] | 10w | 23.855 |  | 0
F | Over Time | 38056.9035 | 36948.45 | [5 empty] | 19075.35 | [11 empty] | B/Fluid 424 | 69.785 |  | 0
2.2 | EQUIPMENT | 1024107.966 | 713074.912 | [5 empty] | 835061.5017 | -121986.5897 | [10 empty] | Grease 30722 | 28.26 |  | 0
2.2.1 | OWN | 712345.75 | 434504.7 | [5 empty] | 516890.055 | -82385.355 | [10 empty] | DTE-26 | 13.17 |  | 0
A | Heavy Duty | 645773.75 | 392157.7 | [5 empty] | 433233.255 | [11 empty] | 15w40 Shell | 20.3 |  | 0
B | Trucks | 29682 | 18547 | [5 empty] | 55746 | [11 empty] | DTE-25 | 14.374 |  | 0
C | Vehicle | 8330 | 8330 | [5 empty] | 8400 | [11 empty] | ATX | 26.5013 |  | 0
D | Crusher Plant | 28560 | 15470 | [5 empty] | 2981.55
E | Auxillary | 0 | [6 empty] | 16529.25 | 0 | [10 empty] | 80W90 | 26.265 |  |  | 5 | [7 empty] | 37500 | 358125 | Own | 460674 | 4606.74
2.2.2 | RENTAL | 311762.216 | 278570.212 | [5 empty] | 318171.4467 | -39601.2347 | [24 empty] | Rental | 0
A | Heavy Duty | 119600 | 84644 | [5 empty] | 67595 | [6 empty] | WEEKLY RENTAL EQUIPMENTS COST |  |  |  |  | KEROSINE | 5.75 |  | 0 | [5 empty] | Fuel rental | [9 empty] | Lubrelicant
B | Trucks | 50800 | 85269.652 |  |  |  |  | 59660 | 189626.4467 | [6 empty] | ___SURVEYING |  |  |  |  | Benzin | 10.5 |  | 0 | [5 empty] | Equipment | No of Equi. | Op.h | No of Days In A Week | Total hrs. in a week | p/h | Nafta | Total Fuel Cost | Rental Reate | Total Rent Cost
C | Vehicle | 51100 | 26600 | [5 empty] | 60950 | [6 empty] | __TOTAL STATION=350*7=2450 |  |  |  |  | AC50 | 33.405 |  | 0
D | Crusher Plant | [14 empty] | ___ | ___OTHERS=902*7=6314 |  |  |  | Ep 3 | 41.14 |  | 0 | [5 empty] | Dozer |  | 8 | 6 | 0 | 45 | 0 | 0 | 850 | 0
E | Dump Trucks Per Km | 90262.216 | 82056.56 | [5 empty] | 1.3347 | [6 empty] | ____LAB.EQTS =404.8*7=2833.60 |  |  |  |  | Az011068 | 24.335 |  | 0 | [5 empty] | Grader |  | 8 | 6 | 0 | 18 | 0 | 0 | 550 | 0
2.3 | SPARE PART, TYRE& TUBE | 0 | 0 | [5 empty] | 88557.1105 | -88557.1105 | [10 empty] | Ep 2 | 41.387 |  | 0 |  |  | 2450 |  |  | Smooth roller | 1 | 1 | 6 | 6 | 8 | 48 | 458.4 | 280 | 1680
A | Spare Part | 0 | [6 empty] | 52789.2205 | [7 empty] | 2450 |  |  |  | Gx90 | 16.67 |  | 0 |  |  | 6314 |  |  | Small Vehicle | 18 | 8 | 6 | 864 | 3 | 2592 | 24753.6 | 50 | 43200
B | Tyre & Tube | 0 | [6 empty] | 35767.89 | [7 empty] | 6314 | [6 empty] | 0 |  |  | 2833.6 |  |  | Loader | 1 | 8 | 6 | 48 | 18 | 864 | 8251.2 | 450 | 21600
2.4 | FUEL | 399532.2392 | 263721.48 | [5 empty] | 363797.7 | -100076.22 | [6 empty] | 2833.6 | [12 empty] | Air compressor |  | 8 | 6 | 0 | 15 | 0 | 0 | 5 | 0
A | Own | 260326.5592 | 195047.12 | [5 empty] | 229496.05 | [7 empty] | 11597.6 | [12 empty] | Excavator |  | 8 | 6 | 0 | 18 | 0 | 0 | 550 | 0
B | Rental | 139205.68 | 68674.36 | [5 empty] | 134301.65 | [20 empty] | Crusher |  | 8 | 6 | 0 | 2 | 0 | 0 | 50 | 0
2.5 | LUBRICANT (Engine Oil(15 W40,Grease ,10W, 85w140,Battery Water & Benzene) | 55538.593 | 50489.63 | [5 empty] | 1623.915 | 48865.715 | [19 empty] | Water Pump |  | 4 | 6 | 0 | 0.5 | 0 | 0 | 5 | 0
A | Own | 55538.593 | 50489.63 | [5 empty] | 1623.915 | [20 empty] | Robin Vibrator |  | 8 | 6 | 0 | 0.5 | 0 | 0 | 5 | 0
B | Rental | 0 | [6 empty] | 0 | [20 empty] | Dump truck | 10 | 8 | 6 | 480 | 10 | 4800 | 45840 | 160 | 76800
2.6 | CONSTRUCTION MATERIAL | 48662.625 | 44238.75 | [5 empty] | 16817.6 | 27421.15 | [19 empty] | Shower truck own |  | 8 | 6 | 0 | 10 | 0 | 0 | 66.6667 | 0
A | Main Road | 48662.625 | 44238.75 | [5 empty] | 0 | [20 empty] | Cargo truck | 3 | 8 | 6 | 144 | 10 | 1440 | 13752 | 120 | 17280
B | Camp Construction | 0 | [6 empty] | 16817.6 | [27 empty] | 0
| 1)Contractor | 0 | 0 | [5 empty] | 16817.6 |  | 1175000% | [25 empty] | 0
| 2)Consultant | [7 empty] | 0 | [27 empty] | 0
2.7 | General items | 13306.593 | 12044.63 | [5 empty] | 26281.98 | -14237.35 | [26 empty] | 0
| Laboratory Test | 345 | 300 | [5 empty] | 3478.98 | [27 empty] | 0
| Maintenance Cost | 287.5 | 250 | [5 empty] | 6992 | -6742 | [26 empty] | 0
| Traveling Perdium | 690 | 600
| Rental Driver Over Time | 3113.55 | 2830.5
| Consultant Allowance(Over time) | 8705.543 | 7914.13 | [5 empty] | 15000 | [27 empty] | 0
| Loading & UnLoading | 165 | 150 | [26 empty] | Generator |  | 8 | 6 | 0 | 5 | 0 | 0 | 2 | 0
| Total | 1824457.8903 | 1361785.372 |  |  | 2514309.1959 | 1669120.7125 |  | 1576844.8872 | -215059.5152 | [19 empty] | MIXER |  | 8 | 6 | 0 | 2 | 0 | 0 | 20 | 0
DIRECT COST |  |  | Plan by Direct cost |  | Actual by Direct cost | [31 empty] | 0
|  |  | #REF! |  | #REF! | [24 empty] | Fuel truck |  | 8 | 6 | 0 | 4 | 0 | 0 | 66.6667 | 0
0
Prepared By ______________________ |  |  | Checked By _____________________ |  |  | Approved By _____________________ | [23 empty] | Shower truck |  | 8 | 6 | 0 | 6 | 0 | 0 | 66.6667 | 0
[30 empty] | Total | [6 empty] | 93055.2 |  | 120420 | 1204.2
|  | 271952.2 |  |  | 852260.4017 | -903210.3364 | 2214045.7737
2094327.2378
|  | plan(income-expense) | 689851.3056 | Actual(income-expense) | 307335.3405 |  |  |  | 2080000%
890941.8173
1886695.7737
6210
—
13050
Prepared By______________________
Fasil N.
49 |  |  |  |  | Checked By_______________________ |  |  |  | Plan Income |  |  |  |  | Actual Income
[6 empty] | Natan K |  |  | 2514309.1959 |  |  |  |  | 1669120.7125
Approved By_______________________
ABEL N.
74459
|  |  | 1.4558 | 0.6869
149465.601
63181.37

## summery(new)2
Cross-land Construction Company
|  | Project: Haro sebu-Lelo-Qaqe | [10 empty] | NEXT
|  | WEEKLY INCOME -EXPENSE SUMMERY | [10 empty] | CONSTRUCTION | 153091.328
[6 empty] | Week 32 ((23-29)-08-07) | [6 empty] | SPARE PART | 24763
[6 empty] | Project Cost |  | VAT 15% | Total Project Cost
[6 empty] | 227468548.36 |  | 34120282.254 | 261588830.614
INCOME |  |  |  |  | EXPENSE
DESCRIPTION |  | AMOUNT |  | ACCOMPLISHMENT IN PERCENT | DESCRIPTION | AMOUNT |  | REMARK |  | Week 32 ((23-29)-08-07) INCOME |  | Week 32 ((23-29)-08-07) EXPENSE
GENERAL & PRELIMINARY |  | 2750 |  | 0.001209% | BASIC SALARY | 196869.57 |  |  |  | GENERAL & PRELIMINARY | 2750 |  | 196869.57 | 1968.6957
SITE CLEARANCE |  | 0 |  | 0% | OVERE TIME | 68806 |  |  |  | SITE CLEARANCE | 0 | OVERE TIME | 68806 | 23.83
DRAINAGE |  | 53558.9239 |  | 0.02355% | TOTAL MANPOWER | 265675.57 |  |  |  | DRAINAGE | 53558.9239 | TOTAL MANPOWER | 265675.57 | 1992.5257 | 1992.5257
EARTH WORK |  | 1296414.28 |  | 0.5699% | OWEN EQUIPMENT | 444704.7 |  |  |  | EARTH WORK | 1296414.28 | OWEN EQUIPMENT | 444704.7
SUB-BASE AND R. BASE |  | 0 |  | 0% | RENTAL EQUIPMENT | 272035.032 |  |  |  | SUB-BASE AND R. BASE | 0 | RENTAL EQUIPMENT | 272035.032
STRUCTURES |  | 180434.9095 |  | 0.07932% | TOTAL EQUIPMENT | 716739.732 |  |  |  | STRUCTURES | 180434.9095 | TOTAL EQUIPMENT | 716739.732
ANCILLARY WORKS |  | 0 |  | 0% | FUEL | 341481.68 |  |  |  | ANCILLARY WORKS | 0 | FUEL | 341481.68
PRODUCTION |  | 52883.1977 |  | 0.02325% | LUBRICANT | 51352.13 |  |  |  | PRODUCTION | 52883.1977 | LUBRICANT | 51352.13
HAULING(Earth works) |  | 83079.4014 |  | 0.03652% | SPARE PARTS | 0 |  |  |  | HAULING(Earth works) | 83079.4014 | SPARE PARTS | 0
[5 empty] | CONSTRUCTION MATERIAL | 126223.92 | [5 empty] | CONSTRUCTION MATERIAL | 126223.92
TOTAL INCOME |  | 1669120.7125 |  | 0.7338% | OTHERS | 13847.5 | [5 empty] | OTHERS | 13847.5
[5 empty] | TOTAL EXPENSE | 1515320.532
Profit(income-expense)= |  | 153800.1805
profit+own equipment= |  | 598504.8805 | [9 empty] | 167509.57
Less Retention (5%)= |  | 83456.0356 | [9 empty] | 161531.157 | 5978.413 |  | 341481.68
Less loanRepayment(1O%)= |  | 166912.0713
Net cash inflow this week |  | 348136.7736 | [11 empty] | miscellaneous | 5978.41
[14 empty] | pipe cement | 16192
[10 empty] | 1608586.4 |  |  |  | pipe rebar | 16515.104
Prepared by___________ |  |  | Checked By____________ |  |  | Approved by__________________ | [7 empty] | concrete cement | 53556.8
| Fasil N. |  |  | Natan K. |  |  | AMARE M. | [6 empty] | paved cement | 10458.36
102700.674
| less advance | 667648.285
| retention | 83456.0356
| with hold | 33382.4143
| bank loan | 221158.4944 | [9 empty] | 62.1
|  | -407140.3488 | [9 empty] | 480.024
[11 empty] | 12722.4 | 127.224 | 57250.8 | concrete
[13 empty] | 1088.1 | paved
[13 empty] | 24187.95 | massonery
[13 empty] | 27945 | pipe
110471.85
-15752.07
drainage
[12 empty] | 18 | 54018.57
[12 empty] | 19 | 84188.63
[12 empty] | 20 | 98225.94
[12 empty] | 21 | 104489.81
[12 empty] | 22 | 96227.99
0
437150.94
[12 empty] | CEMENT | CONCRETE | 90
[13 empty] | PAVED | 1.953
[13 empty] | MASSONERY | 65.918
[13 empty] | PIPE | 64.4
REBAR
[14 empty] | 222.271 | 97799.24 | 49601.672
[14 empty] | 191 |  | 108653
84040
[9 empty] | BASIC SALARY | 0 | [5 empty] | 59051.328
[9 empty] | OVERE TIME | 0
[9 empty] | TOTAL MANPOWER | 0
[9 empty] | OWEN EQUIPMENT | 0 |  |  |  | 156850.568
[9 empty] | RENTAL EQUIPMENT | 0
[9 empty] | TOTAL EQUIPMENT | 0
[9 empty] | FUEL | 56093.8 |  |  |  |  | 143091.328
[9 empty] | LUBRICANT | 5609.38
[9 empty] | SPARE PARTS | 0 |  |  |  | 199656.372
|  | INCOME Vs EXPENSE | [6 empty] | CONSTRUCTION MATERIAL | 0
[8 empty] | GENERAL & PRELIMINARY | OTHERS | 0
[8 empty] | SITE CLEARANCE | 0
[8 empty] | DRAINAGE | 0
[8 empty] | EARTH WORK | 61451.6
[8 empty] | SUB-BASE AND R. BASE | 0
[8 empty] | STRUCTURES | 0
[8 empty] | ANCILLARY WORKS | 0
[8 empty] | PRODUCTION | 59874.75
[8 empty] | HAULING(Earth works) | 0

## Weekly Ms
Cross-land Construction Company
Project: Haro sebu-Lelo-Qaqe
WEEKLY MACHINERY STATUS
Week 32 ((23-29)-08-07)
NO | OWN | QTY | OPERATION | IDLE | DOWN | FUEL(total) | mob.n(hr.) | Standard Consumption | Fuel per hr. | REMARK(idle case)
1 | Dozer | 3 | 230.48 | 74.66 | 0.33 | 11101 |  |  | 48.1647 | Fuel Charging ,Rain Case & Mechanical Problem
2 | Grader | 1 | 47.83 | 11.2 | 0 | 624 |  |  | 13.0462 | Fuel Charging ,Rain Case & Shower Truck Case
3 | Roller | 2 | 34.33 | 61 | 0 | 285 |  |  | 8.3018 | Rain Case & Being activity dependent
4 | Loader | 4 | 115.82 | 73.08 | 0 | 1450 |  |  | 12.5194 | Fuel Charging ,Operator Sick & Rain Case
5 | Excavator | 1 | 38.5 | 15.8 | 0 | 586 |  |  | 15.2208 | Rain Case
6 | Crusher | 1 | 32.5 | 24.5 | 0 | 21 |  |  | 0.64615 | Stone Stocking & Rain Case
7 | Dump truck | 2 | 102 | 10 | 48 | 645 |  |  | 6.3235 | Rain Case & Mechanical Problem
8 | Water truck | 3 | 104 | 19 | 0 | 396 |  |  | 3.8077 | Rain Case
9 | Generator | 3 | 92 | 0 | 0 | 70 |  |  | 0.76087
10 | Mixer | 3 | 0 | 0 | 0 | 0 |  |  | 0
11 | Vibrator | 3 | 0 | 0 | 0 | 0 |  |  | 0
12 | Small vehicle | 1 | 70 | 0 | 0 | 0 |  |  | 0 |  | 3414
13 | Air Compressor | 1 | 0 | 0 | 0 | 0 |  |  | 0
14 | Hand compactor |  | 0 | 0 | 0 | 0 |  |  | 0
15 | Water Pump | 1 | 0 |  |  | 0 |  |  | 0
| SUB TOTAL |  |  |  |  | 15178
RENTAL
1 | Loader | 1 | 45.49 | 0.27 | 0 | 591 |  |  | 12.9919 | Fuel Charging
2 | Dump truck | 5 | 140.96 | 5.19 | 0 | 915 |  |  | 6.4912 | Spond Clearing
3 | Dozer | 1 | 0 | 0 | 0 | 0 |  |  | 0
4 | Grader | 1 | 42.34 | 2 | 0 |  |  |  | 0 | Shower Truck Case
5 | BackLoader | 1 | 55 | 0 | 0 | 184 |  |  | 3.3455
5 | Small vehicle | 5 | 210 | 0 | 0 | 675 |  |  | 3.2143
6 | Water truck | 1 | 88 | 0 | 0 | 350 |  |  | 3.9773
| SUB TOTAL |  |  |  |  | 2715
|  |  |  | GRAND TOTAL |  | 17893
| Prepared By: ________________ |  |  | Checked By____________________ | [5 empty] | Approved By: ___________________
| Fasil N. |  |  |  |  | NATAN K. |  |  |  | AMARE M.
| Average trip of Owned D / Truck = ___________________ |  |  | trips
| Average trip of Rental D / Truck = ___________________ |  |  | trips

## Lab. Evalu.
Cross-land Construction Company
Project: Haro sebu-Lelo-Qaqe
Weekly Evaluation of Labour Utilization
Week 32 ((23-29)-08-07)
SN | Activity Description | Unit | Hourly Output | Total MH | Excuted Qty | Expected Qty | Required MH | Operator Eff. | Skilled Labour |  | Required Vs Actual | Remark
[9 empty] | Required | Actual
|  |  | 1 | 2 | 3 | 4=(2*1) | 5=(3/1) | 6=(3/4) | (7)=(5)/10 |  | 9=(7/6)
MASON
1 | Class 'B' Masonry(Major) | m3 | 0.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Class 'B' Masonry(Minor) | m3 | 0.19 | 390 | 45.51 | 74.1 | 239.5263 | 61.42% | 23.9526 | 39 | 0.61417
3 | Class 'C' Concrete(Minor) | m3 | 1.87 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | Class"A" concrete(Major) | m3 | 0.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Class"A" concrete(Minor) | m3 | 0.46875 |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | Paved Water Way | m2 | 1 | 110 | 85.6 | 110 | 85.6 | 77.82% | 8.56 | 11 | 0.77818
7 | Pipe Installation | pc | 0.3125 |  |  | 0 | 0 | 0 | 0 | 0 | 0
8 | Pipe production | pc | 2.4 |  |  | 0 | 0 | 0 | 0 | 0 | 0
9 | Back fill | m3 | 0.125 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  |  | 0 | 0 | 0 |  | 0 |  |  | 0
| CARPENTER |  |  | 0 | 0 | 0
| Form work(Major) | m2 | 1.125 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Form work(Minor) | m2 | 2.25 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| False work(Major) | m2 | 0.02375 |  |  |  |  | 0 | 0 | 0 | 0
| False work(Minor) | m2 | 0.21875 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| TOTAL |  |  |  | 0 |  |  | 0 |  |  | 0
| BAR BENDER |  |  |  | 0 |  |  | 0 |  |  | 0
| Re-bar bending & placing(major) | kg | 50 | 73 | 3623.536 | 3650 | 72.4707 | 99.27% | 7.2471 | 7.3 | 99.27%
| Re-bar bending for pipe | kg | 14.26 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Prepared By___________________ |  |  |  | Checked By___________________ |  |  |  |  | Approved By_________________________________________
| Fasil N. |  |  |  |  | Natan k. |  |  |  |  | AMARE M.

## Cons.Mat.Evalu.
Cross-land Construction Company
Project: Haro sebu-Lelo-Qaqe
Weekly Evaluation of Construction Material Utilization
Week 32 ((23-29)-08-07)
SN | Description | Unit | Executed Qty |  | Consumption Qty(Qun) |  | Standard Consumption (qtl/unit) | Expected Qty |  | Unit Rate | Difference
[11 empty] | This week |  | To date
|  |  | This Week | To date | This Week | To date |  | This week | To date |  | Qty | Amt | Qty | Amt
CEMENT
1 | Class 'B' Masonry | m3 | 45.51 | 0 | 57 | 0 | 1.17 | 53.2467 | 0 |  | 3.7533 | 0 | 0 | 0 | Inefficient
| Lean Concrete | m3 | 5.8 | 0 | 15 | 0 | 2.5 | 14.5 | 0 |  | 0.5 | 0 | 0 | 0 | Under Usage
2 | Class A Concrete | m3 | 0 |  | 0 | 0 | 4 | 0 | 0 |  | 0 | 0 | 0 | 0 | Efficient
3 | Paved Water Way | m2 | 85.6 | 0 | 7 | 0 | 0.15 | 12.84 | 0 |  | -5.84 | 0 | 0 | 0 | Under Usage
4 | Pipe production | No. |  | 0 |  | 0 | 1.48 | 0 | 0 |  | 0 | 0 | 0 | 0 | Efficient
| F36" | No. |  | 0 |  | 0 | 1.05 | 0 | 0 |  | 0 | 0 |  |  | Efficient
| F42" | No. |  | 0 |  | 0 | 1.43 | 0 | 0 |  | 0 | 0 |  |  | Efficient
| F48" | No. |  | 0 |  | 0 | 1.52 | 0 | 0 |  | 0 | 0 |  |  | Efficient
5 | Pipe Installation | No. |  | 0 |  | 0 | 0.15 | 0 | 0 |  | 0 | 0 |  |  | Efficient
| TOTAL |  |  |  | 79 | 0 |  | 80.5867 | 0 |  | -1.5867 | 0 | 0 |  | Under Usage
| Paved Ditch Pointing | qun | 88.52 |  | 14.5 | [5 empty] | 14.5 | 0 | 0
| Nail | Kg | [8 empty] | 0 | 0 | 0
| Equlaptes tree | Pc | [8 empty] | 0 | 0 | 0
| Angle Iron | [9 empty] | 0 | 0 | 0
| Black Iron wire | Kg | [8 empty] | 0 | 0 | 0
| Reinforcement Bar | Kg | 3623.536 | [7 empty] | 0 | 0 | 0
| Explosive Material | [9 empty] | 0 | 0 | 0
| Dynamic Goma | Kg | [8 empty] | 0 | 0 | 0
| Anfo | Kg | [8 empty] | 0 | 0 | 0
| Electric Detonator | Pc(6m) | [8 empty] | 0 | 0 | 0
|  | Pc(4m) | [8 empty] | 0 | 0 | 0
| Fuel | lt | [8 empty] | 0 | 0 | 0
| Lubricant | lt | [8 empty] | 0 | 0 | 0
| Grease | lt | [8 empty] | 0 | 0 | 0
Prepared By_____________________________ |  |  |  | Checked By___________________________ |  |  |  |  | Approved By_______________
| Fasil N. |  |  |  | Natan k. |  |  | AMARE M.

## Weekly Surveying Rep.
Cross-land Construction Campany
Project:-Haro Sabu Lello Qaqe
Surveying Weekly Report
Week 32 ((23-29) 08-2007)
Act. No. | Work Description |  | Location | Remark
1 | Settingout Center line |  | 13+960-14+340,16+300-16+600,16+700-16+740,11+220-11+520,12+66013+060,8+570 | Section-3
2 | Slope Stake for embankement |  | 11+200-11+520 | Section-3
3 | Subgrade bluetop |  | 16+320-16+460,13+480-13+740,15+820-15+300,16+940-17+040,14+380-14+600,12+900-13+160,13+460 | Section-3
4 | paved Ditch level & layout |  | 8+570-8+995 | Section-2
5 | Stractural Work |  | 2+695,21+546 | Section-2
6 | Blue top For G-7 |  | 10+840-11+000 | Section 3
7 | Blue top For G-20 |  | 17+060-17+260 | Section 3
8 | Asbuilt Reading For G-20 |  | 10+380-10+520 | Section-3
9 | Asbuilt Reading For G-7 |  | - | Section-3
10 | Subgrade Asbuilt Reading |  | 13+480-14+300,15+820-16+320 | Section-3
11 | Excavation Slope stake& Checking |  | 16+700-16+740,16+640-16+680 | Section-3
12 | payment Reading |  | 10+640-11+300 | Section-2
13 | payment Reading |  | 18+780-19+100,19+300-19+460,20+180-20+340,13+480,16+000-16+320 | Section-3
| Prepered By__________________ |  | Checked By___________________ | Approved By_______________
| AREGAWI G/E. |  | NATAN K. | AMARE M.

## Weekly Store Balance Report
Cross-Land Construction Company
Project: Haro Sebu-Lello-Qaqe
Weekly Store Balance Sheet
Week 32 (23/08/07-29/08/07)
No. | Item |  | Unit | Previous Week Balance | Issued Quantity | Received Qty | To date Stock Balance | Issued Quantity Date:- 23/08/07 | Previous Date Balance | Issued Quantity Date:-24/08/07 | Received Qty | To date Stock Balance | Previous Date Balance | Issued Quantity Date:- 25/08/07 | Received Qty | To date Stock Balance | Previous Date Balance | Issued Quantity Date:- 26/08/07 | Received Qty | To date Stock Balance | Previous Date Balance | Issued Quantity Date:- 27/08/07 | Received Qty | To date Stock Balance | Previous Date Balance | Issued Quantity Date:- 28/08/07 | Received Qty | To date Stock Balance | Issued Quantity Date:- 29/08/07 | To date Weekly Issued Balance | To date Weekly Stock Balance | Remark
1 | Construction Material
| a) Cement Opc |  | Quintal. | 219 | [24 empty] | 25 | 25 | 194
| a) Cement Ppc |  | Quintal. | 348 |  |  |  | 60 |  | 70 | [11 empty] | 30 | [7 empty] | 160 | 188
| b) Sand |  | m3 | 0 |  | 48 | [22 empty] | 48 | 48 | 0
| c) Aggregate | [28 empty] | 0 | 0
| i.00 |  | m3 | 0 | [25 empty] | 0 | 0
| ii.01 |  | m3 | 128 | [25 empty] | 0 | 128
| iii.02 |  | m3 | 475 |  |  |  | 18 | [21 empty] | 18 | 457
| iv.03 |  | m3 | 176 | [25 empty] | 0 | 176
| v.Over Size |  | m3 | [26 empty] | 0 | 0
| d) Reinfocement Bar | [28 empty] | 0 | 0
| i.Ø6 |  | Roll/kg | [26 empty] | 0 | 0
| ii.Ø8 |  | Pcs | 100 | [25 empty] | 0 | 100
| iii.Ø10 |  | Pcs | 0 | [25 empty] | 0 | 0
| iv.Ø12 |  | Pcs | 235 | [25 empty] | 0 | 235
| v.Ø14 |  | Pcs | 30 | [25 empty] | 0 | 30
| vi.Ø16 |  | Pcs | 330 | [25 empty] | 0 | 330
| vii.Ø20 |  | Pcs | 25 | [25 empty] | 0 | 25
| viii.Ø24 |  | Pcs | 0 | [25 empty] | 0 | 0
| ix.Ø30 |  | Pcs | [26 empty] | 0 | 0
| x.Ø32 |  | Pcs | 54 | [24 empty] | 54 | 54 | 0
| xi.Black Wire | 1.5 |  | 75 | [25 empty] | 0 | 75
|  | 2.5 | Roll | 0 | [25 empty] | 0 | 0
3 | Oil &Lubricant | [28 empty] | 0 | 0
| 15W40 |  |  | 449 |  |  |  | 59 |  | 73 | [11 empty] | 30 | [6 empty] | 65 | 227 | 222 | 53(Rental)
| 10W |  |  | 647 | [24 empty] | 213 | 213 | 434 | 5(Rental)
| 85W140 |  |  | 65 | [24 empty] | 57 | 57 | 8
| 85W90 |  |  | 369 | [25 empty] | 0 | 369
| AZZOLA 46 |  |  | 267 | [25 empty] | 0 | 267
| 30W |  |  | 0 | [25 empty] | 0 | 0
| 50W |  |  | 208 | [25 empty] | 0 | 208
| Grease |  |  | 53 |  |  |  | 17 | [5 empty] | 3 | [14 empty] | 17 | 37 | 16 | 3(Rental)
| Coolant |  |  | 33 | [25 empty] | 0 | 33
| Stearing Fluid |  |  | 19 | [25 empty] | 0 | 19
| Break Fluid |  |  | 23 | [17 empty] | 0.5 | [7 empty] | 0.5 | 22.5 | 0.5(Rental)
| Battery Water |  |  | 14 | [25 empty] | 0 | 14
| Battery Acid |  |  | 46 | [25 empty] | 0 | 46
2 | Production Quantity
| A) Pipe Production | [28 empty] | 0 | 0
| i. Ø36 |  | Pcs | [26 empty] | 0 | 0
| ii. Ø42 |  | Pcs | 56 |  |  |  | 8 | [21 empty] | 8 | 48
| iii.Ø48 |  | Pcs | 0 | [25 empty] | 0 | 0
3 | Eucaliptus tree | 10-12cm | Pcs | 0 | [25 empty] | 0 | 0
|  | 6-8cm |  | 0 | [25 empty] | 0 | 0
|  | 2-4cm | Pcs | 0 | [25 empty] | 0 | 0
| Timber |  | Pcs | 0 | [25 empty] | 0 | 0
4 | Fuel Balnce | [28 empty] | 0 | 0
| A) Gas oil |  | Lit. | 48634.5 |  |  |  | 4104 |  | 4660 | [7 empty] | 4019 |  |  |  | 3236 |  |  |  | 2095 |  |  | 2793 | 20907 | 27727.5
| B) Benzene |  | Lit. | 18 |  | 100 |  | 10 | [9 empty] | 20 | [10 empty] | 13 | 43 | 75
|  | Prepared By Samson Tibebu | [11 empty] | Checked By____________________________ | [14 empty] | Approved By________________________
|  | Signature_______________________________________ | [11 empty] | Signature_______________________________________ | [14 empty] | Signature__________________________________

## Weekly Labratory Report
Cross-land Construction Campany
Project:-Haro Sabu Lello Qaqe
Weekly Labratory Report
Week-32 (23/08/07-29/08/07)
Act. N. | Type of Activity | Material Suitability |  |  | Location
1 | FDT Test | Enbankement |  |  | 11+240-11+520
|  | Sub- grade |  |  | 13+740-14+100,14+100-14+300,13+440-14+720,15+800-16+300
|  | Back fill |  |  | 7+660,17+848
|  |  |  | G-20 | 7+000-7+100,10+340-10+540,3+320-3+800
2 | Take of sampel | Masonry ston |  |  | 10+700,14+750,21+500
3 | Take of sampel | Agg 02,03 |  |  | C-plant(ERA Roade 5.2km)
4 | Compressive Strength of Concrete | Slab casting |  |  | 10+629
6 | CBR Pentration | Borrow(capping) |  |  | 12+389.5
7 | Lean concrete cast checking | bottom |  |  | 21+500(lelo side)
8 | Absorption test socking | Masonry ston |  |  | 14+750,21+500,10+700
9 | Gradation Test | 02,03 |  |  | C-plant(ERA Roade 5.2km)
10 | Plastic index | Borrow,Cut section |  |  | 12+389.5,17+940
11 | Gradation Washing & sieve for soil classification | Borrow(capping) |  |  | 5+500
12 | CBR Socking | Borrow,Cut section |  |  | 17+940
Prepered By__________________ |  | Checked By___________________ |  |  | Approved By_______________
| YIGREMACHEW Y. |  | Natan K. |  | Amare M.